TEMPLATE FOR FINANCIAL PROPOSAL

INDIVIDUAL CONSULTANT FOR Breastfeeding and BFHI Training Consultant

Currency of the proposal: USD

| S. No. | Deliverables | Deadline for completion of deliverable | Details of Travel Required | Professional Fee (Daily) | Input Days | Total Professional Fee |  | Total Travel Cost |  | Total Amount (All Inclusive Fee) |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | (A) | (B) | (C) | (D) | (E) | (F = DxE) |  | (G) |  | (H = F+G) |  |
| 1. | Approved inception report with desk-review findings, consultation summary, confirmed target groups and facilities, methodology, detailed workplan, training coverage plan, quality standards, monitoring approach and risk mitigation. | 10 November 2026 | Travel to Tonga upon approval of inception report | Click here | Click here | Click here |  | Click here |  | Click here |  |
| 2. | MoH and UNICEF-approved orientation and competency-based training package, including facilitator guide, presentations, participant materials, practical exercises, pre/post tests, competency checklists, attendance template and session evaluation form | 20 November 2026 | Do Not Fill | Click here | Click here | Click here |  | Do Not Fill |  | Click here |  |
| 3. | i) Policy orientation delivered to clinical nurses and other relevant staff at Vaiola Hospital who previously received breastfeeding capacity-building support, including TOT for master trainers /facility champions ii) Comprehensive breastfeeding and BFHI training, incorporating policy requirements, delivered to health workers in outer island hospitals (Vava’u hospital, Ha’apai Hospital, and Eua hospital) including TOT for master trainers / facility champions iii) Training report submitted, including participant records, pre- and post-training assessments, recommendations, and remaining capacity-building needs. | 31 December 2026 | Do Not Fill | Click here | Click here | Click here |  | Do Not Fill |  | Click here |  |
| 4. | Train public health nurses and identified master trainers on breastfeeding counselling, management of common breastfeeding difficulties, and post-discharge support. Develop and roll out breastfeeding counselling tools, referral pathways, and supportive supervision guidance to support continuity of breastfeeding care through routine postnatal and immunization services. | 31 December 2026 | Do Not Fill | Click here | Click here | Click here |  | Do Not Fill |  | Click here |  |
| 5. | Final report approved by MoH and UNICEF documenting results, participant reach, competency findings, lessons, gaps and recommendations. Annexes include an MoH-owned rollout plan, orientation/refresher schedule, supervision and monitoring framework, and all final editable tools/materials. | 30 April 2027 | Do Not Fill | Click here | Click here | Click here |  | Do Not Fill |  | Click here |  |
|  | TOTAL AMOUNT |  |  |  |  |  |  |  |  |  | Click here |  |

Note: Shaded cells shall be filled by the Applicants.

Notes to financial offer:

- Payment will be made on submission and acceptance of deliverables as stated above. UNICEF reserves the right to withhold payment in case the deliverables submitted are not up to the required standard or in case of delays in submitting the deliverables on the part of the consultant.

- Air travel should be economy class using the most direct route.

- No other fee would be paid or reimbursed other than the fee indicated in the financial proposal.

- The consultant will work on own computer(s) and use own office resources and materials in the execution of this assignment, including personal email address(es) and phones.

- All pocket expenses including travel will be included in the specific lumpsum deliverables fees and paid as part of satisfactory completion of the deliverables. If the deliverables are not completed or achieved, these costs will not be paid separately.

PAYMENT TERMS: Net 30 days

Name of the Applicant: Click here

Signature of the Applicant: Click here

Address:  Click here

Contact no.:  Click here

Email address:  Click here

Date: Click here