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TEMPLATE FOR FINANCIAL PROPOSAL

INDIVIDUAL CONSULTANT FOR
Senior Public Finance and Refugee Inclusion Costing Consultant (International/National)
Currency of the proposal: USD
(ETB will be paid for Nationals)

	S. No.
	Deliverables
	Deadline for completion of deliverable
	Details of Travel Required
	Professional Fee (Daily)


	Input Days
	Total Professional Fee 
	Total Travel Cost 
	Total Amount (All Inclusive Fee) 

	
	(A)
	(B)
	(C)
	(D)
	(E)
	(F = DxE)
	(G)
	(H = F+G)

	1.
	Refined methodology; Sector and data availability assessment; Stakeholder mapping; Workplan; Interview guides; Facility costing templates; Consultation tools; Data-request templates.
	15.11.2026
	NA
	Click here
	Click here
	Click here
	NA
	Click here

	2.
	Three weeks (or 4 weeks depending on the number of refugee hosting areas to be selected for the study during the inception phase) of field research completed to assess the situation and multi-sector social service delivery gaps plus available data collection; Service delivery (plus management) and financing mapping; Unit costs; Incremental costs; Financing gaps; Delivery of practical workshops for jointly defining minimum standards/packages, costing assumptions, costing exercises and use of costing models (travel to Ethiopia required); Preliminary findings.
	31.01.2027
	Phase 1: 7 working days in Addis
Ababa to meet with stakeholders;
and discuss with partners to set
the minimum standards/packages
and yearly milestones by sector.
7 days (including travel time)
each to visit 3 refugee hosting
areas (i.e. 21 days in total) to
Asayita (Afar Region), Kebribeyah
(Somali Region), and a Refugee
Hosting Area under the RRS
Melkadida Branch Office (Somali
Region)) to assess the situation
and multi-sector social service
delivery gaps plus available data
collection.

Phase 2: 5 working days in Addis
Ababa for a workshop with
partners for a consensus on
costing assumptions and
conducting costing exercises
	Click here
	Click here
	Click here
	Click here
	

	3.
	Revised costing analysis; Cost-of-inaction analysis; Targeted cost-effectiveness analysis; one week visit in Addis to conduct validation workshop and agree with RRS on policy recommendation and framing of policy brief.
	31.04.2027
	5 working days in Addis Ababa
for a workshop on costing
exercises with partners, as well
as a validation workshop with
stakeholders
	Click here
	Click here
	Click here
	Click here
	Click here 

	4.
	Refugee inclusion investment case; Policy brief; PowerPoint slides, Validation workshop report; Replicable costing framework (reusable costing tools and guidance materials) and capacity-building completion note.
	30.06.2027
	NA
	Click here
	Click here
	Click here
	NA
	

	
	TOTAL AMOUNT 
	
	
	Click here



Note: Shaded cells shall be filled by the Applicants.



Notes to financial offer:
1. Payment will be made on submission and acceptance of deliverables as stated above. UNICEF reserves the right to withhold payment in case the deliverables submitted are not up to the required standard or in case of delays in submitting the deliverables on the part of the consultant.
2. Air travel should be economy class using the most direct route.
3. No other fee would be paid or reimbursed other than the fee indicated in the financial proposal.
4. The consultant will work on own computer(s) and use own office resources and materials in the execution of this assignment, including personal email address(es) and phones. 
5. All pocket expenses including travel will be included in the specific lumpsum deliverables fees and paid as part of satisfactory completion of the deliverables. If the deliverables are not completed or achieved, these costs will not be paid separately.

PAYMENT TERMS: Net 30 days

Name of the Applicant: Click here
Signature of the Applicant: Click here 	
Address:  Click here
Contact no.:  Click here	
Email address:  Click here
Date: Click here
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