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TEMPLATE FOR FINANCIAL PROPOSAL

INDIVIDUAL CONSULTANT FOR Communication Associate Consultant– EU-funded Social Protection (EU4PEOPLE) and Roma Inclusion Programmes (36 months)

Currency of the proposal: BAM

	S. No.
	Deliverables
	Deadline for completion of deliverable
	Details of Travel Required
	Professional Fee (Daily)


	Input Days
	Total Professional Fee 
	Total Travel Cost 
	Total Amount (All Inclusive Fee) 

	
	(A)
	(B)
	(C)
	(D)
	(E)
	(F = DxE)
	(G)
	(H = F+G)

	
1.
	Updated EU4PEOPLE C&V Plan and 2027 communication workplan 
Joint UN content plan for 2027 agreed with UNDP, UNFPA and ILO 
Annual event calendar for 2027 cleared with EUD 
	26.02.2027 
	NA
	Click here
	Click here
	Click here
	Click here
	Click here

	2.
	UNICEF inputs to the UNDP-led joint C&V Plan (initial) 
UNICEF component communication plan for 2027 
	31.03.2027 
	NA
	Click here
	Click here
	Click here
	Click here
	

	3.
	Min. 3 events planned and managed, each with event package and post-event report 
Min. 60 social media posts and 12 web items published 
6 human-interest stories and 3 short videos 
2 newsletters and min. 3 fact sheets/brochures 
Min. 5 joint UN comms meetings with action points; 2 branding spot-check notes 
Progress report with media/social media analytics 
	30.06.2027 
	NA
	Click here
	Click here
	Click here
	Click here
	Click here 

	4.
	Min. 24 social media posts and 3 web items on UNICEF-led components 
3 human-interest stories and 1 short video 
Community-facing material set for 1 campaign 
UNICEF content and messages for International Roma Day (8 April) 
Progress report incl. C&V inputs to joint reporting 
	15.07.2027 
	NA
	Click here
	Click here
	Click here
	Click here
	

	5.
	Min. 3 events planned and managed, each with event package and post-event report 
Min. 60 social media posts and 12 web items published 
6 human-interest stories and 3 short videos 
2 newsletters and min. 3 fact sheets/brochures 
Min. 5 joint UN comms meetings; 2 branding spot-check notes 
C&V section of the annual EU progress report (consolidated with partner agencies) 
	15.12.2027 
	NA
	Click here
	Click here
	Click here
	Click here
	

	6.
	Min. 24 social media posts and 3 web items on UNICEF-led components 
3 human-interest stories and 1 short video 
Community-facing material set for 1 campaign 
UNICEF content/speakers for 1 joint event led by UNDP 
C&V inputs for UNICEF components to the joint annual report 
	22.12.2027 
	NA
	
	
	
	
	

	7.
	Updated EU4PEOPLE C&V Plan and 2028 communication workplan 
Joint UN content plan for 2028 agreed with UNDP, UNFPA and ILO 
Annual event calendar for 2028 cleared with EUD 
	26.02.2028 
	NA
	
	
	
	
	

	8.
	UNICEF inputs to the UNDP-led joint C&V Plan (annual update) 
UNICEF component communication plan for 2028 
	31.03.2028 
	NA
	
	
	
	
	

	9.
	Min. 3 events planned and managed, each with event package and post-event report 
Min. 60 social media posts and 12 web items published 
6 human-interest stories and 3 short videos 
2 newsletters and min. 3 fact sheets/brochures 

Min. 5 joint UN comms meetings with action points; 2 branding spot-check notes 
Progress report with media/social media analytics 
	30.06.2028 
	NA
	
	
	
	
	

	10.
	Min. 24 social media posts and 3 web items on UNICEF-led components 
3 human-interest stories and 1 short video 
Community-facing material set for 1 campaign 
UNICEF content and messages for International Roma Day (8 April) 
Progress report incl. C&V inputs to joint reporting 
	15.07.2028 
	NA
	
	
	
	
	

	11.
	Min. 3 events planned and managed, each with event package and post-event report 
Min. 60 social media posts and 12 web items published 
6 human-interest stories and 3 short videos 
2 newsletters and min. 3 fact sheets/brochures 
Min. 5 joint UN comms meetings; 2 branding spot-check notes 
C&V section of the annual EU progress report (consolidated with partner agencies) 
	15.12.2028 
	NA
	
	
	
	
	

	12.
	Min. 24 social media posts and 3 web items on UNICEF-led components 
3 human-interest stories and 1 short video 
Community-facing material set for 1 campaign 
UNICEF content/speakers for 1 joint event led by UNDP 
C&V inputs for UNICEF components to the joint annual report 
	22.12.2028 
	NA
	
	
	
	
	

	13.
	Updated EU4PEOPLE C&V Plan and 2029 communication workplan 
Joint UN content plan for 2029 agreed with UNDP, UNFPA and ILO 

Annual event calendar for 2029 cleared with EUD 

	26.02.2029 
	NA
	
	
	
	
	

	14.
	UNICEF inputs to the UNDP-led joint C&V Plan (annual update) 
UNICEF component communication plan for 2029 
	31.03.2029 
	NA
	
	
	
	
	

	15.
	Min. 3 events planned and managed, each with event package and post-event report 
Min. 60 social media posts and 12 web items published 
6 human-interest stories and 3 short videos 
2 newsletters and min. 3 fact sheets/brochures 
Min. 5 joint UN comms meetings with action points; 2 branding spot-check notes 
Progress report with media/social media analytics 
	30.06.2029 
	NA
	
	
	
	
	

	16.
	Min. 24 social media posts and 3 web items on UNICEF-led components 
3 human-interest stories and 1 short video 
Community-facing material set for 1 campaign 
UNICEF content and messages for International Roma Day (8 April) 
Progress report incl. C&V inputs to joint reporting 
	15.07.2029 
	NA
	
	
	
	
	

	18.
	Min. 24 social media posts and 3 web items on UNICEF-led components 
3 human-interest stories and 1 short video 
Community-facing material set for 1 campaign 
UNICEF content/speakers for 1 joint event led by UNDP 
C&V inputs for UNICEF components to the joint annual report 
End-of-assignment summary for UNICEF components 
	17.12.2029 
	NA
	
	
	
	
	

	
	TOTAL AMOUNT 
	
	
	Click here



Note: Shaded cells shall be filled by the Applicants.



Notes to financial offer:
1. Payment will be made on submission and acceptance of deliverables as stated above. UNICEF reserves the right to withhold payment in case the deliverables submitted are not up to the required standard or in case of delays in submitting the deliverables on the part of the consultant.
2. Air travel should be economy class using the most direct route.
3. No other fee would be paid or reimbursed other than the fee indicated in the financial proposal.
4. The consultant will work on own computer(s) and use own office resources and materials in the execution of this assignment, including personal email address(es) and phones. 
5. All pocket expenses including travel will be included in the specific lumpsum deliverables fees and paid as part of satisfactory completion of the deliverables. If the deliverables are not completed or achieved, these costs will not be paid separately.

PAYMENT TERMS: Net 30 days

Name of the Applicant: Click here
Signature of the Applicant: Click here 	
Address:  Click here
Contact no.:  Click here	
Email address:  Click here
Date: Click here
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