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TEMPLATE FOR FINANCIAL PROPOSAL

INDIVIDUAL CONSULTANT FOR Multiple and Flexible Pathways for Adolescents Consultant

Currency of the proposal: USD

	S. No.
	Deliverables
	Deadline for completion of deliverable
	Details of Travel Required
	Professional Fee (Daily)


	Input Days
	Total Professional Fee 
	Total Travel Cost 
	Total Amount (All Inclusive Fee) 

	
	(A)
	(B)
	(C)
	(D)
	(E)
	(F = DxE)
	(G)
	(H = F+G)

	
1.
	Deliverable 1  Inception report and analytical framework. Confirms the pathway types in scope, the age band, the case selection criteria and evidence grading standard, the architecture of the guidance package, and the workplan. Presented to the section for sign-off before analysis begins.
	15.12.2026
	
	Click here
	Click here
	Click here
	Click here
	Click here to add text or click the + sign to add more rows

	2.
	Deliverable 2 Multiple and Flexible Pathways Evidence update: what has changed since 2020. Working paper reviewing the evidence, policy and delivery landscape for flexible pathways since the publication of the current global guidance, covering protracted displacement, learning loss and recovery, digital and remote delivery modalities, and the financing environment.

	15.02.2027
	
	Click here
	Click here
	Click here
	Click here
	

	3.
	Deliverable 3 Documented models. Ten to twelve programme cases documented against a common template and graded transparently against the agreed evidence standard, distinguishing evaluated, promising and documented-but-unevaluated models. Includes two country visits of five days each to observe delivery and verify documentation.
	 30.04.2027
	Travel fee
The Consultant is expected to travel to some of the countries to provide consultations and technical support.
	Click here
	Click here
	Click here
	Click here
	Click here to add text or click the + sign to add more rows

	4.
	Deliverable 4 Certification and equivalency module. Regulatory scan across the PROSPECTS countries establishing, for each, what a non-formal or accelerated certificate entitles a learner to do next and who decides, including age-and-grade re-entry policy, national qualifications framework placement, TVET admission rules, and whether eligibility differs by legal status. Sets out regulatory options with worked country examples and a readiness diagnostic a ministry can apply to itself.
	30.06.2027
	

	Click here
	Click here
	Click here
	Click here
	

	5.
	Deliverable 5 Technical design guidelines. Design parameters and two to three contextlinked archetypes rather than a single model, covering programme design, teaching and learning, learner support and wellbeing, certification and onward pathways, governance and financing, and a facilitator competency profile. Written to be usable inside and beyond PROSPECTS and structured as a companion to the existing global guidance. Technical design guidelines. Design parameters and two to three contextlinked archetypes rather than a single model, covering programme design, teaching and learning, learner support and wellbeing, certification and onward pathways, governance and financing, and a facilitator competency profile. Written to be usable inside and beyond PROSPECTS and structured as a companion to the existing global guidance.
	31.08.2027
	
	Click here
	Click here
	Click here
	Click here
	

	6.
	Deliverable 6 Validation, final package and presentation. One facilitated session with country offices and the wider community of practice, final guidance package incorporating feedback, and a presentation deck for strategic and advocacy use.
	15.10.2027.
	
	
	
	
	
	

	
	TOTAL AMOUNT 
	
	
	Click here



Note: Shaded cells shall be filled by the Applicants.



Notes to financial offer:
1. Payment will be made on submission and acceptance of deliverables as stated above. UNICEF reserves the right to withhold payment in case the deliverables submitted are not up to the required standard or in case of delays in submitting the deliverables on the part of the consultant.
2. Air travel should be economy class using the most direct route.
3. No other fee would be paid or reimbursed other than the fee indicated in the financial proposal.
4. The consultant will work on own computer(s) and use own office resources and materials in the execution of this assignment, including personal email address(es) and phones. 
5. All pocket expenses including travel will be included in the specific lumpsum deliverables fees and paid as part of satisfactory completion of the deliverables. If the deliverables are not completed or achieved, these costs will not be paid separately.

PAYMENT TERMS: Net 30 days

Name of the Applicant: Click here
Signature of the Applicant: Click here 	
Address:  Click here
Contact no.:  Click here	
Email address:  Click here
Date: Click here
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