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TEMPLATE FOR FINANCIAL PROPOSAL

INDIVIDUAL CONSULTANT FOR Consultancy on strengthening cholera preparedness, prevention and evidence-based WASH planning following the 2026 outbreak

Currency of the proposal: USD

	S. No.
	Deliverables
	Deadline for completion of deliverable
	Details of Travel Required
	Professional Fee (Daily)


	Input Days
	Total Professional Fee 
	Total Travel Cost 
	Total Amount (All Inclusive Fee) 

	
	(A)
	(B)
	(C)
	(D)
	(E)
	(F = DxE)
	(G)
	(H = F+G)

	
1.
	Inception report with detailed methodology, workplan, stakeholder engagement plan, data requirements, travel plan and risk management.
	4th December 2026
	NA - Online
	Click here
	Click here
	Click here
	NA
	Click here

	2.
	Completed and validated 2026 Cholera After-Action Review (AAR) report for Borno and Yobe States, documenting key findings, lessons learned, operational and coordination gaps, and prioritized recommendations with responsible institutions and indicative timelines.
	8th January 2027
	Mission travel
Trip 1 of 2 (covers Workstreams 1 and 2): 


1 round trip from home base to Maiduguri via Abuja, 12 days, 4 to 15 January 2027: - Maiduguri, Borno State: 6 days - Damaturu, Yobe State: 3 days - Yola, Adamawa State: 3 days 

Workstream 1 in-country: AAR workshops and validation 
in Maiduguri and Damaturu, completed by 8 January 2027. Desk review and remote key informant interviews online in December 2026. 



Covered under Trip 1 (4 to 15 January 2027): field verification of priority hotspots and validation of findings with state authorities and partners in Maiduguri, Damaturu and Yola, completed by 15 January 2027. 

	Click here
	Click here
	Click here
	Click here

	

	3.
	Final cholera micro-hotspot analysis report for Borno, Adamawa and Yobe States, including methodology, maps and profiles of priority hotspots, recurrent transmission patterns, key WASH and contextual risk factors, and prioritized areas for cholera prevention and preparedness. Findings presented and validated with relevant government and partner stakeholders in BAY States.

	15th January 2027
	
	Click here
	Click here
	Click here
	
	Click here 

	4.
	A prioritized cholera prevention and WASH investment framework outlining phased interventions, indicative costs, institutional responsibilities, resource mobilization opportunities and targeted capacity-strengthening actions.

	February 15th 2027
	
Mission travel, not office-based in Maiduguri. Trip 2 of 2 (covers Workstreams 3 and 4): 1 round trip from home base to Maiduguri via Abuja, 10 days in early February 2027, completed before 15 February 2027: - Maiduguri, Borno State: 6 
days - Damaturu, Yobe State: 2 days - Yola, Adamawa State: 2 days Workstream 3 in-country: consultations and validation of the investment framework with state authorities and partners. Drafting and costing online. 

In-country work covered under Trip 2 (early February 2027): consultations with state authorities in Maiduguri, Damaturu and Yola on existing coordination arrangements, roles and activation triggers. Validation and handover sessions online in March 2027. 

	Click here
	Click here
	Click here
	Click here

	

	5.
	Validated government-led cholera preparedness and coordination transition package, including institutional responsibilities, activation triggers, coordination procedures, capacity-strengthening priorities and a phased implementation roadmap.

	15th March 2027
	
	Click here
	Click here
	Click here
	
	

	6.
	Consolidated final consultancy deliverables incorporating feedback from the supervisor and steering committee, accompanied by a technical handover note documenting key findings, priority actions, institutional responsibilities and recommendations for follow-up by UNICEF and relevant government counterparts.

	30th March 2027
	NA
	Click here
	Click here
	Click here
	NA
	

	
	TOTAL AMOUNT 
	
	
	Click here



Note: Shaded cells shall be filled by the Applicants.



Notes to financial offer:
1. Payment will be made on submission and acceptance of deliverables as stated above. UNICEF reserves the right to withhold payment in case the deliverables submitted are not up to the required standard or in case of delays in submitting the deliverables on the part of the consultant.
2. Air travel should be economy class using the most direct route.
3. No other fee would be paid or reimbursed other than the fee indicated in the financial proposal.
4. The consultant will work on own computer(s) and use own office resources and materials in the execution of this assignment, including personal email address(es) and phones. 
5. All pocket expenses including travel will be included in the specific lumpsum deliverables fees and paid as part of satisfactory completion of the deliverables. If the deliverables are not completed or achieved, these costs will not be paid separately.

PAYMENT TERMS: Net 30 days

Name of the Applicant: Click here
Signature of the Applicant: Click here 	
Address:  Click here
Contact no.:  Click here	
Email address:  Click here
Date: Click here
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