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TEMPLATE FOR FINANCIAL PROPOSAL

INDIVIDUAL CONSULTANT FOR Sanitation Finance Consultant

Currency of the proposal: USD – for internationals /NGN – for nationals

	S. No.
	Deliverables
	Deadline for completion of deliverable
	Details of Travel Required
	Professional Fee (Daily)


	Input Days
	Total Professional Fee 
	Total Travel Cost 
	Total Amount (All Inclusive Fee) 

	
	(A)
	(B)
	(C)
	(D)
	(E)
	(F = DxE)
	(G)
	(H = F+G)

	
1.
	Inception report

	30 November 2026
	NA
	Click here
	Click here
	Click here
	NA
	Click here

	2.
	Stakeholder and institutional map (with named focal points and entry points) 

	10 December 2026
	Abuja (if not based there) – 1 trip x 3 days

Lagos (if not based there) – 1 trip x 3 days 

	Click here
	Click here
	Click here
	Click here
	

	3.
	Consolidated source pack (studies, datasets, government documents) indexed, and written comments on the market assessment team inception report.

	15 December 2026
	NA
	Click here
	Click here
	Click here
	NA
	Click here 

	4.
	Financial institution mapping note, with a shortlist recommendation and a note on the role informal savings groups could play as a distribution and repayment channel.

	15 January 2027
	NA
	Click here
	Click here
	Click here
	NA
	

	5.
	Consolidated comments of the draft market assessment, with a written assessment of remaining data gaps.

	15 February 2027
	NA
	Click here
	Click here
	Click here
	NA
	

	6.
	Drafting inputs to the updated Nigeria SPF Country Context Report and to the Nigeria SPF concept note.

	15 March 2027 

	NA
	Click here
	Click here
	Click here
	NA
	

	7.
	Consolidated report with comments on data collection tools and market assessment and business model for bankable models (FSTP & PPP for public places) 

	30 April 2027 

	NA
	Click here
	Click here
	Click here
	NA
	

	8.
	Report that provides review of the financing model (demand estimates, guarantee-sizing inputs, scenarios), and inputs to the TA budget and implementation plan. 
	30 June 2027 
	Abuja (if not based there) – 1 trip x 3 days

Lagos (if not based there) – 1 trip x 3 days 

	Click here
	Click here
	Click here
	Click here
	

	9.
	Final Steering committee composition, terms of reference, and minutes of first two meetings convened 
	15 September 2027 
	Abuja (if not based there) – 2 trips x 3 days each 

	Click here
	Click here
	Click here
	Click here
	

	10.
	National and one state level framework for targeted subsidies developing, including implementation guide 
 
	31 July 2027
	Ondo (if not based there) – 1 trip x 3 days

	Click here
	Click here
	Click here
	Click here
	

	11.
	Written comments on four concept notes and proposals reviewed 

 
	31 August 2027
	Abuja (if not based there) – 1 trip x 3 days
	Click here
	Click here
	Click here
	Click here
	

	12.
	Report on technical assistance provided to development bank projects in at least one state 
	30 September 2027
	Ondo (if not based there) – 2 trips x 3 days each 

	Click here
	Click here
	Click here
	Click here
	

	13.
	Consolidated meeting minutes with follow-up actions  
	31 October 2027
	Abuja (if not based there) – 1 trip x 3 days

Lagos (if not based there) – 1 trip x 3 days 

	Click here
	Click here
	Click here
	Click here
	

	14.
	Two knowledge products of progress and lessons learnt for the development of a bankable model (one for PPPs and one for FSM) 
	10 November 2027
	Bauchi state (if not based there) – 2 trips x 5 days each 

	Click here
	Click here
	Click here
	Click here
	

	15.
	End-of-assignment report (max 10 pages) and handover pack: contact list, document library and updated SPF Project Management tool.

	10 November 2027
	NA
	Click here
	Click here
	Click here
	NA
	

	
	
	
	
	
	
	
	
	

	
	TOTAL AMOUNT 
	
	
	Click here



Note: Shaded cells shall be filled by the Applicants.



Notes to financial offer:
1. Payment will be made on submission and acceptance of deliverables as stated above. UNICEF reserves the right to withhold payment in case the deliverables submitted are not up to the required standard or in case of delays in submitting the deliverables on the part of the consultant.
2. Air travel should be economy class using the most direct route.
3. No other fee would be paid or reimbursed other than the fee indicated in the financial proposal.
4. The consultant will work on own computer(s) and use own office resources and materials in the execution of this assignment, including personal email address(es) and phones. 
5. All pocket expenses including travel will be included in the specific lumpsum deliverables fees and paid as part of satisfactory completion of the deliverables. If the deliverables are not completed or achieved, these costs will not be paid separately.

PAYMENT TERMS: Net 30 days

Name of the Applicant: Click here
Signature of the Applicant: Click here 	
Address:  Click here
Contact no.:  Click here	
Email address:  Click here
Date: Click here
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