## Financial proposal template
TEMPLATE FOR FINANCIAL PROPOSAL
INDIVIDUAL CONSULTANT FOR International Consultancy to develop Uzbekistan’s Integrated Parenting Support Framework (IPF)
Currency of the proposal: USD
S. No | Deliverables | Deadline for completion of deliverable | Details of Travel Required | Professional Fee (Daily) | Input Days | Total Professional Fee | Total Travel Cost | Total Amount (All Inclusive Fee)
| (A) | (B) | (C) | (D) | (E) | (F=D*E) | (G) | (H = F+G)
1 | D1. Inception note with scope, proposed outline, document list, criteria for rapid review, division of responsibilities and workplan agreed with UNICEF. | 15 January 2027 | N/A |  |  |  | N/A
2 | D2. Rapid parenting landscape and strategic gap analysis: inventory/matrix of existing packages and standards/SOPs, coverage and institutional mapping, prioritized gaps and opportunities for harmonization. | 20 July 2027 | N/A |  |  |  | N/A
3 | D3. Draft Integrated Parenting Support Framework, including cross-sectoral architecture, proposed continuum of support, coordination arrangements, integration of behavioural evidence, and indicative phased roadmap. | 15 September 2027 | N/A |  |  |  | N/A
| D4. Tashkent technical validation: draft IPF presented and discussed with relevant stakeholders; structured feedback and revisions log prepared. | 15 November 2027 | 1 mission to Tashkent, 4 days.
| D5. Final IPF and implementation package, comprising the endorsed/revised framework draft, prioritized action matrix, proposed coordination responsibilities and high-level monitoring indicators. | 15 December 2027 |  |  |  |  | N/A
| TOTAL AMOUNT | [5 empty] | 0 | 0
Note: Shaded cells shall be filled by the Applicants
Notes to financial offer:
1 | Payment will be made on submission and acceptance of deliverables as stated above. UNICEF reserves the right to withhold payment in case the deliverables submitted are not up to the required standard or in case of delays in submitting the deliverables on the part of the consultant.
2 | Air travel should be economy class using the most direct route.
3 | No other fee would be paid or reimbursed other than the fee indicated in the financial proposal.
4 | The consultant will work on own computer(s) and use own office resources and materials in the execution of this assignment, including personal email address(es) and phones.
5 | All pocket expenses including travel will be included in the specific lumpsum deliverables fees and paid as part of satisfactory completion of the deliverables. If the deliverables are not completed or achieved, these costs will not be paid separately.
PAYMENT TERMS: Net 30 days
Name of the Applicant:
Signature of the Applicant: ​
Address: ​
Contact no.:
Email address:
Date: