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TEMPLATE FOR FINANCIAL PROPOSAL

INDIVIDUAL CONSULTANT FOR Digital Health Financing and Investment Consultant (Multi-country)
 

Currency of the proposal: USD

	S. No.
	Deliverables
	Deadline for completion of deliverable
	Details of Travel Required
	Professional Fee (Daily)


	Input Days
	Total Professional Fee 
	Total Travel Cost 
	Total Amount (All Inclusive Fee) 

	
	(A)
	(B)
	(C)
	(D)
	(E)
	(F = DxE)
	(G)
	(H = F+G)

	
1.
	Inception report (no more than 10 pages): work plan, country allocation and methods agreed with the companion consultancy, country-by-country division of drafting and review with institutional partners, and the register method.
	28 February 2027
	
	Click here
	Click here
	Click here
	Click here
	Click here

	2
	Baseline financing window register for the eight blueprint countries (spreadsheet with a summary note of no more than 5 pages).
	31 March 2027
	
	
	
	
	
	

	3
	Three quarterly register updates (updated spreadsheet with a note of no more than 3 pages flagging windows at risk).
	31 December 2027
	
	
	
	
	
	

	4
	Two quarterly register updates (updated spreadsheet with a note of no more than 3 pages flagging windows at risk).
	30 June 2028
	
	
	
	
	
	

	5
	Four country financing situation analyses (10 to 15 pages each).
	Four by 30 April 2027
	
	
	
	
	
	

	6
	Four country financing situation analyses (10 to 15 pages each).
	Four by 30 June 2027
	
	
	
	
	
	

	7
	Financing and costing content for seven investment blueprints, drafted or reviewed as recorded in the inception report.
	Seven by 15 December 2027
	
	
	
	
	
	

	8
	Financing and costing content for one investment blueprints, drafted or reviewed as recorded in the inception report.
	One by 15 June 2028
	
	
	
	
	
	

	9
	Twelve technical review notes on institutional partner deliverables (2 to 4 pages each), each within ten working days of receipt.
	Final note by 30 June 2028
	
	
	
	
	
	

	10
	Six technical advisory notes responding to country office requests prioritised by the contract manager (2 to 5 pages each).
	Final note by 30 June 2028
	
	
	
	
	
	

	11
	Five IFI engagement products (brief or positioning note of 2 to 4 pages, plus a one-page note of agreed actions after the engagement).
	Five by 30 June 2027
	
	
	
	
	
	

	12
	Six IFI engagement products (brief or positioning note of 2 to 4 pages, plus a one-page note of agreed actions after the engagement).
	Six by 31 December 2027 (eleven cumulative)
	
	
	
	
	
	

	13
	Five IFI engagement products (brief or positioning note of 2 to 4 pages, plus a one-page note of agreed actions after the engagement).
	Five by 30 June 2028 (sixteen cumulative)
	
	
	
	
	
	

	14
	Quarterly progress reports (no more than 3 pages, reporting against the performance indicators) with inputs to Steering Committee materials.
	31 March, 30 June, 30 September and 31 December 2027 
	
	
	
	
	
	

	15
	Quarterly progress reports (no more than 3 pages, reporting against the performance indicators) with inputs to Steering Committee materials.
	31 March and 30 June 2028
	
	Click here
	Click here
	Click here
	Click here
	

	16

	Two expansion opportunity assessments for non-participating countries agreed in writing with the contract manager (8 to 10 pages each).
	Two by 31 December 2027
	
	
	
	
	
	

	17
	Two expansion opportunity assessments for non-participating countries agreed in writing with the contract manager (8 to 10 pages each).
	Two by 31 May 2028
	
	
	
	
	
	

	18
	One financing concept note for regional public goods financed jointly by governments and IFIs (no more than 10 pages each).
	30 September 2027 
	
	
	
	
	
	

	19
	One financing concept note for regional public goods financed jointly by governments and IFIs (no more than 10 pages each).
	31 March 2028
	
	
	
	
	
	

	20
	Final learning and handover report (no more than 20 pages), including reusable tools, examples and content for case studies.
	30 June 2028
	
	
	
	
	
	

	21
	Travel is undertaken only on missions approved in advance by the contract manager and is reimbursed on actual costs in line with UNICEF policy for consultants (economy class by the most direct route, with daily subsistence allowance at prevailing UN rates). For the financial proposal, candidates provide an indicative travel budget, itemised by trip and calculated from their place of residence, against the planned missions below, each of about one week (five working days at the destination plus travel days). The indicative budget is used to compare proposals and is not a lump sum; actual missions, destinations and frequency are set in the work plan and may change.
	30.06.2028
	
	
	
	
	
	

	
	TOTAL AMOUNT 
	
	
	Click here



Note: Shaded cells shall be filled by the Applicants.



Notes to financial offer:
1. Payment will be made on submission and acceptance of deliverables as stated above. UNICEF reserves the right to withhold payment in case the deliverables submitted are not up to the required standard or in case of delays in submitting the deliverables on the part of the consultant.
2. Air travel should be economy class using the most direct route.
3. No other fee would be paid or reimbursed other than the fee indicated in the financial proposal.
4. The consultant will work on own computer(s) and use own office resources and materials in the execution of this assignment, including personal email address(es) and phones. 
5. All pocket expenses including travel will be included in the specific lumpsum deliverables fees and paid as part of satisfactory completion of the deliverables. If the deliverables are not completed or achieved, these costs will not be paid separately.

PAYMENT TERMS: Net 30 days

Name of the Applicant: Click here
Signature of the Applicant: Click here 	
Address:  Click here
Contact no.:  Click here	
Email address:  Click here
Date: Click here
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