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TEMPLATE FOR FINANCIAL PROPOSAL

INDIVIDUAL CONSULTANT FOR Digital Health Systems and Interoperability Consultant (Multi-country)
 

Currency of the proposal: USD

	S. No.
	Deliverables
	Deadline for completion of deliverable
	Details of Travel Required
	Professional Fee (Daily)


	Input Days
	Total Professional Fee 
	Total Travel Cost 
	Total Amount (All Inclusive Fee) 

	
	(A)
	(B)
	(C)
	(D)
	(E)
	(F = DxE)
	(G)
	(H = F+G)

	
1.
	Inception report (no more than 10 pages): work plan, country allocation and methods agreed with the companion consultancy, country-by-country division of drafting and review with institutional partners, and the maturity assessment framework.
	31 March 2027
	
	Click here
	Click here
	Click here
	Click here
	Click here

	2
	Three situation analyses for the implementation countries (10 to 15 pages each).
	30 April 2027
	
	
	
	
	
	

	3
	One national requirements and architecture packages for the HIE enabling layers, each revised following national validation coordinated through the country office.
	31 May 2027
	
	
	
	
	
	

	4
	One national requirements and architecture packages for the HIE enabling layers, each revised following national validation coordinated through the country office.
	31 May 2027
	
	
	
	
	
	

	5
	One national requirements and architecture packages for the HIE enabling layers, each revised following national validation coordinated through the country office.
	31 July 2027
	
	
	
	
	
	

	6
	Fourteen technical review notes on institutional partner deliverables (2 to 4 pages each), each within ten working days of receipt.
	Final note by 31 July 2028
	
	
	
	
	
	

	7
	Four digital health maturity and architecture assessments for blueprint countries (8 to 12 pages each).
	31 May 2027
	
	
	
	
	
	

	8
	Four digital health maturity and architecture assessments for blueprint countries (8 to 12 pages each).
	31 July 2027
	
	
	
	
	
	

	9
	Requirements, architecture and sequencing content for eight investment blueprints, drafted or reviewed as recorded in the inception report. (7 total)
	Seven by 15 December 2027
	
	
	
	
	
	

	10
	Requirements, architecture and sequencing content for eight investment blueprints, drafted or reviewed as recorded in the inception report. (1 total)
	Eighth by 15 June 2028
	
	
	
	
	
	

	11
	Ten technical advisory notes responding to requests from participating country offices, prioritised by the contract manager (2 to 5 pages each).
	Final note by 31 July 2028
	
	
	
	
	
	

	12
	Three quarterly progress reports (no more than 3 pages, reporting against the performance indicators), including country inputs to the financing window register prepared with the companion consultant.
	30 June, 30 September and 31 December 2027
	
	
	
	
	
	

	13
	Two quarterly progress reports (no more than 3 pages, reporting against the performance indicators), including country inputs to the financing window register prepared with the companion consultant.
	31 March and 30 June 2028
	
	
	
	
	
	

	14
	Two technical inputs, with documented recommendations, to the digital components of IFI operations in non-participating countries agreed in writing with the contract manager (4 to 6 pages each).
	Two by 31 December 2027
	
	
	
	
	
	

	15
	Two technical inputs, with documented recommendations, to the digital components of IFI operations in non-participating countries agreed in writing with the contract manager (4 to 6 pages each).
	Two by 30 June 2028
	
	Click here
	Click here
	Click here
	Click here
	

	16

	Technical design notes for shared multi-country infrastructure as regional public goods, specifying architecture, governance arrangements, financing models and opportunities (no more than 15 pages).
	31 October 2027 
	
	
	
	
	
	

	17
	Technical design notes for shared multi-country infrastructure as regional public goods, specifying architecture, governance arrangements, financing models and opportunities (no more than 15 pages).
	30 April 2028
	
	
	
	
	
	

	18
	Final learning and handover report, including technical documentation needed by institutional partners (no more than 20 pages plus annexes).
	31 July 2028
	
	
	
	
	
	

	19
	Travel is undertaken only on missions approved in advance by the contract manager and is reimbursed on actual costs in line with UNICEF policy for consultants (economy class by the most direct route, with daily subsistence allowance at prevailing UN rates). For the financial proposal, candidates provide an indicative travel budget, itemised by trip and calculated from their place of residence, against the planned missions below, each of about one week (five working days at the destination plus travel days). The indicative budget is used to compare proposals and is not a lump sum; actual missions, destinations and frequency are set in the work plan and may change.
	As approved, to 31 July 2028
	
	
	
	
	
	

	20
	Travel
	31.07.2028
	
	
	
	
	
	

	
	TOTAL AMOUNT 
	
	
	Click here



Note: Shaded cells shall be filled by the Applicants.



Notes to financial offer:
1. Payment will be made on submission and acceptance of deliverables as stated above. UNICEF reserves the right to withhold payment in case the deliverables submitted are not up to the required standard or in case of delays in submitting the deliverables on the part of the consultant.
2. Air travel should be economy class using the most direct route.
3. No other fee would be paid or reimbursed other than the fee indicated in the financial proposal.
4. The consultant will work on own computer(s) and use own office resources and materials in the execution of this assignment, including personal email address(es) and phones. 
5. All pocket expenses including travel will be included in the specific lumpsum deliverables fees and paid as part of satisfactory completion of the deliverables. If the deliverables are not completed or achieved, these costs will not be paid separately.

PAYMENT TERMS: Net 30 days

Name of the Applicant: Click here
Signature of the Applicant: Click here 	
Address:  Click here
Contact no.:  Click here	
Email address:  Click here
Date: Click here
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