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TEMPLATE FOR FINANCIAL PROPOSAL

INDIVIDUAL CONSULTANT FOR: Climate Finance and Partnership Consultant
 

Currency of the proposal: USD

	S. No.
	Deliverables
	Deadline for completion of deliverable
	Details of Travel Required
	Professional Fee (Daily)


	Input Days
	Total Professional Fee 
	Total Travel Cost 
	Total Amount (All Inclusive Fee) 

	
	(A)
	(B)
	(C)
	(D)
	(E)
	(F = DxE)
	(G)
	(H = F+G)

	
1.
	1.1. Updated Legal Due Diligence annex and Term Sheet; documented consulting company feedback and technical QA; integrated workplan, risk and decision logs, and institutional review status

	30-Dec-26

	N/A

	Click here
	Click here
	Click here
	Click here
	Click here

	2.
	1.2. Consolidated proposal package and government and partner validation and endorsement records, covering executing entity roles, governance, cofinancing, operational costs and sustainability; internal clearance and resubmission status.

	16-Jan-27

	N/A

	Click here
	Click here
	Click here
	Click here
	

	3.
	1.3. Updated GCF comment and response matrix, revised proposal documents and progress report covering review issues and outstanding decisions.

	16-Feb-27

	Senegal mission (1 trip, 10 days)

	Click here
	Click here
	Click here
	Click here
	Click here 

	4
	1.4. Consolidated CIC and ITAP review responses, updated proposal package, and project-specific Board documentation and management briefing inputs coordinated with Deliverable 5, according to the confirmed review schedule.

	16-Jun-27

	N/A

	
	
	
	
	

	5
	1.5. Updated review response matrix, proposal and decision records, including any further review or Board preparation actions required under the confirmed schedule

	16-Sep-27

	N/A

	
	
	
	
	

	6
	1.6. Final decision and next-steps record. If approved, transition package covering approval conditions, responsible teams, legal arrangements and implementation readiness; otherwise, pending review actions and responsibilities.
	16-Dec-27

	N/A

	
	
	
	
	

	7
	2.1. Written reviews and proposed text for priority GCF concept notes and proposals agreed in the workplan, integrating locally led adaptation and meaningful, inclusive and safe child and youth-led action into design, consultations, implementation, budgets, results and monitoring; draft checklist, model text and examples.

	16-Apr-27

	N/A

	
	
	
	
	

	8
	2.2. Completed practical guidance package; additional proposal reviews; record of coordination with programme teams, PPR and GenU/Green Rising, including identified GCF opportunities; at least one documented country-office knowledge-sharing session. Adaptation Fund partnership content coordinated under Deliverable 6.

	16-Jul-27

	N/A

	
	
	
	
	

	9
	2.3. Consolidated proposal reviews and final record of guidance application, coordination outcomes and lessons.

	16-Oct-27

	N/A

	
	
	
	
	

	10
	3.1. Draft updated approval/FAA guidance and proposal review SOP; Senegal-based proposal templates and SharePoint microsite structure agreed with PPR and Climate CoE.

	16-Mar-27

	N/A

	
	
	
	
	

	11
	3.2. Consultation-revised guidance, SOP and templates; operational SharePoint microsite with indexed materials and review records.

	16-Jun-27

	N/A

	
	
	
	
	

	12
	3.3. Country-office kick-off and implementation-risk follow-up packages for projects reaching FAA signature; updated guidance and repository reflecting lessons.

	16-Sep-27

	N/A

	
	
	
	
	

	13
	3.4. Final guidance, SOP, templates and repository; consolidated record of country-office kick-offs, risk follow-up and lessons, as applicable to portfolio milestones

	16-Dec-27

	N/A

	
	
	
	
	

	14
	4.1. Monthly NYHQ PPR working session package, interdivisional consultation record and action follow-up. Initial review and clearance tracker and agreed coordination workplan. Outputs reflect the proposal stages reached.

	16-Jan-27

	N/A

	
	
	
	
	

	15
	4.2. Monthly NYHQ PPR working session package, interdivisional consultation record and action follow-up. Certificate of Internal Authority and funding package review records for proposals at the relevant stage. Outputs reflect the proposal stages reached.

	16-Feb-27

	N/A

	
	
	
	
	

	16
	4.3. Monthly NYHQ PPR working session package, interdivisional consultation record and action follow-up. Consolidated Term Sheet, fee proposal and cofinancing consultation records. Outputs reflect the proposal stages reached.

	16-Mar-27


	N/A

	
	
	
	
	

	17
	4.4. Monthly NYHQ PPR working session package, interdivisional consultation record and action follow-up. Recommendations for funding package sign-off and FAA signature where ready, with Legal clearance recorded. Outputs reflect the proposal stages reached.

	16-Apr-27

	N/A

	
	
	
	
	

	18
	4.5. Monthly NYHQ PPR working session package, interdivisional consultation record and action follow-up. Updated clearance tracker and consolidated outstanding review issues. Outputs reflect the proposal stages reached.

	16-May-27

	N/A

	
	
	
	
	

	19
	4.6. Monthly NYHQ PPR working session package, interdivisional consultation record and action follow-up. Mid-year review of proposal clearances, co-financing commitments and escalation needs. Outputs reflect the proposal stages reached.

	16-Jun-27

	N/A

	
	
	
	
	

	20
	4.7. Monthly NYHQ PPR working session package, interdivisional consultation record and action follow-up. Updated proposal review and institutional clearance packages. Outputs reflect the proposal stages reached.

	16-Jul-27

	N/A

	
	
	
	
	

	21
	4.8. Monthly NYHQ PPR working session package, interdivisional consultation record and action follow-up. Documented Term Sheet and fee consultations and cofinancing follow-up. Outputs reflect the proposal stages reached.

	16-Aug-27

	N/A

	
	
	
	
	

	22
	4.9. Monthly NYHQ PPR working session package, interdivisional consultation record and action follow-up. Updated signature recommendations and clearance records for eligible packages. Outputs reflect the proposal stages reached.

	16-Sep-27

	N/A

	
	
	
	
	

	23
	4.10. Monthly NYHQ PPR working-session package, interdivisional consultation record and action follow-up. Consolidated outstanding decisions and interdivisional follow-up. Outputs reflect the proposal stages reached.

	16-Oct-27

	N/A

	
	
	
	
	

	24
	4.11. Monthly NYHQ PPR working-session package, interdivisional consultation record and action follow-up. Documented review lessons and recommended SOP updates for Deliverable 3. Outputs reflect the proposal stages reached.

	16-Nov-27

	N/A

	
	
	
	
	

	25
	4.12. Monthly NYHQ PPR working-session package, interdivisional consultation record and action follow-up. Final clearance tracker, decision record and consolidated funding package recommendations. Outputs reflect the proposal stages reached

	16-Dec-27

	N/A

	
	
	
	
	

	26
	5.1. AMA/RFA consultation and negotiation package, including consolidated positions and outstanding issues; initial readiness oversight tracker and Quarter 1 risk update

	16-Mar-27

	N/A

	
	
	
	
	

	27
	5.2. Updated cooperation agreement consultation package; readiness proposal/grant review records and signature recommendations where ready; Quarter 2 oversight update.

	16-Jun-27

	N/A

	
	
	
	
	

	28
	5.3. Consolidated readiness risk assessments, internal consultation records and recommendations for agreement signature, as applicable.

	16-Aug-27

	N/A

	
	
	
	
	

	29
	5.4. Updated AMA/RFA issues and decision record, readiness grant documentation and Quarter 3 oversight update.

	16-Sep-27

	N/A

	
	
	
	
	

	30
	5.5. Consolidated agreement consultation outcomes and readiness progress, risk and followup records.

	16-Nov-27

	N/A

	
	
	
	
	

	31
	5.6. Final cooperation agreement review package and readiness oversight tracker; Quarter 4 update, outstanding decisions and recommended actions. 
	16-Dec-27

	N/A

	
	
	
	
	

	32
	6.1. Senior-level GCF engagement calendar and briefing packages for agreed engagements, including proposed replenishment support; documented NYHQ management/OED consultations and prioritized opportunity inputs for the climate GPPs workplan.

	16-Dec-27

	N/A

	
	
	
	
	

	33
	6.2. Updated engagement calendar and consolidated briefing and opportunity records for GCF and prioritized climate GPPs; final handover covering repository links, guidance, clearance and readiness trackers, agreement status, pending decisions and next steps.

	16-Dec-27

	N/A

	
	
	
	
	

	
	TOTAL AMOUNT 
	
	
	Click here



Note: Shaded cells shall be filled by the Applicants.



Notes to financial offer:
1. Payment will be made on submission and acceptance of deliverables as stated above. UNICEF reserves the right to withhold payment in case the deliverables submitted are not up to the required standard or in case of delays in submitting the deliverables on the part of the consultant.
2. Air travel should be economy class using the most direct route.
3. No other fee would be paid or reimbursed other than the fee indicated in the financial proposal.
4. The consultant will work on own computer(s) and use own office resources and materials in the execution of this assignment, including personal email address(es) and phones. 
5. All pocket expenses including travel will be included in the specific lumpsum deliverables fees and paid as part of satisfactory completion of the deliverables. If the deliverables are not completed or achieved, these costs will not be paid separately.

PAYMENT TERMS: Net 30 days

Name of the Applicant: Click here
Signature of the Applicant: Click here 	
Address:  Click here
Contact no.:  Click here	
Email address:  Click here
Date: Click here
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