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TEMPLATE FOR FINANCIAL PROPOSAL

INDIVIDUAL CONSULTANT FOR Click here

Currency of the proposal: USD

	S. No.
	Deliverables
	Deadline for completion of deliverable
	Details of Travel Required
	Professional Fee (Daily)


	Input Days
	Total Professional Fee 
	Total Travel Cost 
	Total Amount (All Inclusive Fee) 

	
	(A)
	(B)
	(C)
	(D)
	(E)
	(F = DxE)
	(G)
	(H = F+G)

	
1.
	Del #1: Inception report and detailed workplan for the Mathematics methodology course pilot (methodology, timeline, roles and risk log), endorsed by UNICEF. 
	31 December 2026 

	n/a
	Click here
	6 days
	Click here
	Click here
	Click here

	2.
	Del #2: Pilot implementation framework for the Mathematics methodology course, defining roles, monitoring protocols, Moodle administration/support arrangements, evidence sources and reporting lines across the six pilot universities. 

	31 December 2026 

	n/a
	Click here
	6 days
	Click here
	Click here
	

	3.
	Del #3: Coordination mechanism and stakeholder matrix established with the six partner pedagogical universities, RTMC and MoES; minutes of initial coordination meetings documented and archived. 
	31 December 2026 

	
n/a
	Click here
	5 days
	Click here
	Click here
	Click here 

	4.
	Del #4: First cycle of bi-weekly online coordination and Moodle-supported follow-up completed with Mathematics methodology course instructors (October–November 2026); technical guidance provided on delivery of the first pilot modules; consolidated meeting/action summary shared with RTMC and UNICEF. 
	31 December 2026 

	
n/a
	Click here
	10 days
	Click here
	Click here
	

	5.
	Del #5: Draft classroom observation tool, student/faculty feedback instruments and a protocol for using relevant Moodle participation/completion evidence developed and validated with RTMC. 

	31 December 2026 

	n/a
	Click here
	9 days
	Click here
	Click here
	

	6.
	Del #6: October–November 2026 technical and methodological support provided to the School of Authors, at a minimum input of three working days per month. Support includes piloting and refinement of the informatics-related segment of the School of Authors course; facilitation of assigned online and/or face-to-face activities; review of participants’ assignments and draft products; structured feedback; and contribution to the development, review and piloting of assigned sample fragments of new teaching and learning materials (TLM/UMC). Brief monthly records of activities, outputs, feedback and recommended adjustments submitted. 
	31 December 2026 

	n/a
	
	6 days
	
	
	

	7.
	Del #7: First round of monitoring visits, on-site seminars and coaching sessions conducted across the six pilot universities; structured field reports document faculty participation, implementation evidence, challenges, agreed actions and recommendations. 
	31 March 2027 

	Round 1 monitoring visits: 6 trips (1 per pilot university) x 2 days; 
 Destination: Dushanbe-Khujand, Panjakent, Kulob, Rasht and Bokhtar
	
	14 days
	
	
	

	8.
	Del #8: Practice-oriented training seminar delivered for Mathematics methodology course faculty, using active and game-based methods, microteaching and supervised demonstrations to prepare instructors for piloting the “Organization of Learning Activities” module. Microteaching and model demonstrations are conducted with peers and student-teachers. 
 
	31 March 2027 

	n/a
	
	6 days
	
	
	

	9.
	Del #9: Winter seminar conducted with course instructors to review first-semester piloting of the TLM and Active Learning modules, including Moodle implementation; summary of evidence, feedback and agreed adjustments submitted. 
	31 March 2027 

	n/a
	
	6 days
	
	
	

	10.
	Del #10: Second cycle of bi-weekly online coordination and Moodle-supported follow-up completed (December 2026–February 2027); pilot evidence collected from each of the six universities for the TLM and Active Learning modules. 
	31 March 2027 

	n/a
	
	13 days
	
	
	

	11.
	Del #11: Monitoring and evidence-collection database established, integrating field observations, stakeholder feedback, course products and relevant Moodle activity evidence; first quarterly pilot progress report submitted. 
	31 March 2027 

	n/a
	
	12 days
	
	
	

	12.
	Del #12: December 2026–February 2027 technical and methodological support provided to the School of Authors, at a minimum input of three working days per month. Support includes piloting and refinement of the informatics-related segment of the School of Authors course; facilitation of assigned online and/or face-to-face activities; review of participants’ assignments and draft products; structured feedback; and contribution to the development, review and piloting of assigned sample fragments of new teaching and learning materials (TLM/UMC). Brief monthly records of activities, outputs, feedback and recommended adjustments submitted. 
	31 March 2027 

	n/a
	
	9 days
	
	
	

	13.
	Del #13: Second round of monitoring visits and coaching sessions conducted at the six pilot universities; field monitoring reports with findings and recommendations submitted. 
	30 June 2027 

	Round 2 monitoring visits: 6 trips (1 per pilot university) x 2 days; 
 Destination: Dushanbe-Khujand, Panjakent, Kulob, Rasht and Bokhtar
	
	12 days
	
	
	

	14.
	Del #14: Pilot data collected from each of the six universities for the “Organization of Learning Activities” module; consolidated data analysis report covering the pilot of all three modules. 
	30 June 2027 

	n/a
	
	8 days
	
	
	

	15.
	Del #15: Training/refresher sessions conducted for pilot university faculty on Moodle use, active and game-based learning, facilitation, assessment and revised TLMs; peer learning and mentoring documented.
	30 June 2027 

	n/a
	
	6 days
	
	
	

	16.
	Del #16: Mathematics methodology course modules, programme, syllabus, Moodle structure and assessment tasks revised based on consolidated pilot evidence in collaboration with RTMC national expert teams. 
	30 June 2027 

	n/a
	
	8 days
	
	
	

	17.
	Del #17: Mathematics teaching and learning materials developed, reviewed and finalized, including Grade 8 algebra and geometry workbook materials, competency-based learning tasks and assessment items, selected textbook chapters and accompanying teacher guidance. The materials shall be aligned with the competency-based approach and the methodological principles applied in the new mathematics textbooks and revised based on feedback from the Mathematics working group and piloting evidence.
	30 June 2027 

	n/a
	
	20 days
	
	
	

	18.
	Del #18: March–May 2027 technical and methodological support provided to the School of Authors, at a minimum input of three working days per month. Support includes piloting and refinement of the informatics-related segment of the School of Authors course; facilitation of assigned online and/or face-to-face activities; review of participants’ assignments and draft products; structured feedback; and contribution to the development, review and piloting of assigned sample fragments of new teaching and learning materials (TLM/UMC). Brief monthly records of activities, outputs, feedback and recommended adjustments submitted. A consolidated eight-month implementation note is included with the final monthly record.
	30 June 2027 

	n/a
	
	9 days
	
	
	

	19.
	Del #19: End-of-year seminar conducted with Mathematics methodology course instructors to evaluate the pilot of the “Organization of Learning Activities” module and consolidate overall lessons learned. 
	30 November 2027 

	n/a
	
	6 days
	
	
	

	20
	Del #20: Orientation/training seminars delivered for base-school mentor teachers on use of the revised Mathematics TLMs and on supporting student-teachers during educational and pedagogical practice. 
	30 November 2027 

	Base-school mentor-teacher seminars: 3 trips x 2 days;
 Destination: Dushanbe-Khujand, Panjakent, Kulob, Rasht and Bokhtar
	
	8 days
	
	
	

	21.
	Del #21: Supplementary implementation package completed for the Mathematics methodology course, including Moodle implementation guidance, facilitation materials for active and game-based learning, video scripts and production briefs, reviewed video fragments, and practical guidance for university faculty on the use of the revised course materials.
	30 November 2027 

	n/a
	
	6 days
	
	
	

	22.
	Del #22: Blended and face-to-face components finalized; Moodle course revised and quality-assured; programme, syllabus, video resources and accompanying materials prepared as a publication-ready package. 
	30 November 2027 

	n/a
	
	12 days
	
	
	

	23.
	Del #23: Final pilot evaluation report for the Mathematics methodology course, with recommendations for institutionalization and scale-up, submitted to UNICEF, MoES and RTMC. 
	30 November 2027 

	n/a
	
	10 days
	
	
	

	24.
	Del #24: Recommendations for institutionalization and inputs to the national scale-up plan for the Mathematics methodology course prepared and submitted.
	30 November 2027 

	n/a
	
	8 days
	
	
	

	25.
	Del #25: Final assignment report summarizing key results, lessons learned, risks and recommendations; handover completed. 
	30 November 2027 

	n/a
	
	10 days
	
	
	

	
	TOTAL AMOUNT – 225 working days 
	
	
	Click here



Note: Shaded cells shall be filled by the Applicants.



Notes to financial offer:
1. Payment will be made on submission and acceptance of deliverables as stated above. UNICEF reserves the right to withhold payment in case the deliverables submitted are not up to the required standard or in case of delays in submitting the deliverables on the part of the consultant.
2. Air travel should be economy class using the most direct route.
3. No other fee would be paid or reimbursed other than the fee indicated in the financial proposal.
4. The consultant will work on own computer(s) and use own office resources and materials in the execution of this assignment, including personal email address(es) and phones. 
5. All pocket expenses including travel will be included in the specific lumpsum deliverables fees and paid as part of satisfactory completion of the deliverables. If the deliverables are not completed or achieved, these costs will not be paid separately.

PAYMENT TERMS: Net 30 days

Name of the Applicant: Click here
Signature of the Applicant: Click here 	
Address:  Click here
Contact no.:  Click here	
Email address:  Click here
Date: Click here
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