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TEMPLATE FOR FINANCIAL PROPOSAL

INDIVIDUAL CONSULTANT FOR Click here

Currency of the proposal: PKR

	S. No.
	Deliverables
	Deadline for completion of deliverable
	Details of Travel Required
	Professional Fee (Daily)


	Input Days
	Total Professional Fee 
	Total Travel Cost 
	Total Amount (All Inclusive Fee) 

	
	(A)
	(B)
	(C)
	(D)
	(E)
	(F = DxE)
	(G)
	(H = F+G)

	
1.
	Inception report with a detailed work plan, analysis plan for English, Urdu and Sindhi, and timeline, agreed with NAW/PIE and UNICEF
	13 Nov 2026
	None (remote)
	Click here
	Click here
	Click here
	Click here
	Click here

	2.
	Final NAT technical documentation and inputs for SDG 4.1.1 reporting, reviewed by NAW/PIE
	30 Nov 2026
	None (remote)
	Click here
	Click here
	Click here
	Click here
	

	3.
	Technical note on the extension and completion of FLA administration in English-medium schools (sampling, instruments, quality assurance), where required
	18 Dec 2026
	None (remote)
	Click here
	Click here
	Click here
	Click here
	Click here 

	4.
	Report on the psychometric and statistical analysis of FLS-2026 data (item analysis, reliability, dimensionality) for all three languages
	15 Jan 2027
	None (remote)
	Click here
	Click here
	Click here
	Click here
	

	5.
	Report on scaling, IRT calibration, pilot-to-scale equating and validation, with final scale scores for each language
	29 Jan 2027
	None (remote)
	Click here
	Click here
	Click here
	Click here
	

	6.
	Literacy and numeracy benchmarks for each language, aligned with GPF/MPLs, set through a benchmark-setting workshop with NAW/PIE and documented in a benchmarking report
	12 Feb 2027
	Trip 1: Islamabad, Pakistan – 1 trip, 
7 days. 
	
	
	
	
	

	7.
	Full technical report (methodology, analysis, scaling, benchmarks, interpretation) and SDG 4.1.1 reporting package, validated by NAW/PIE
	26 Feb 2027
	None (remote)
	
	
	
	
	

	8.
	Technical inputs to the national FLS report, plus a presentation of findings to MoFEPT/PIE and stakeholders
	26 Feb 2027
	Trip 2: Islamabad, Pakistan – 1 trip, 
5 days. 

	
	
	
	
	

	9.
	Knowledge-transfer summary listing the sessions delivered, materials and recommendations for future NAW/PIE assessments
	26 Feb 2027
	None
(Delivered during Trips 1 and 2 and remotely)
	
	
	
	
	

	
	TOTAL AMOUNT 
	
	
	Click here



Note: Shaded cells shall be filled by the Applicants.



Notes to financial offer:
1. Payment will be made on submission and acceptance of deliverables as stated above. UNICEF reserves the right to withhold payment in case the deliverables submitted are not up to the required standard or in case of delays in submitting the deliverables on the part of the consultant.
2. Air travel should be economy class using the most direct route.
3. No other fee would be paid or reimbursed other than the fee indicated in the financial proposal.
4. The consultant will work on own computer(s) and use own office resources and materials in the execution of this assignment, including personal email address(es) and phones. 
5. All pocket expenses including travel will be included in the specific lumpsum deliverables fees and paid as part of satisfactory completion of the deliverables. If the deliverables are not completed or achieved, these costs will not be paid separately.

PAYMENT TERMS: Net 30 days

Name of the Applicant: Click here
Signature of the Applicant: Click here 	
Address:  Click here
Contact no.:  Click here	
Email address:  Click here
Date: Click here
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