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TEMPLATE FOR FINANCIAL PROPOSAL

INDIVIDUAL CONSULTANT FOR National Consultants for Child-Sector Data Quality Assurance and Information Governance

Currency of the proposal: USD

	S. No.
	Deliverables
	Deadline for completion of deliverable
	Details of Travel Required
	Professional Fee (Daily)


	Input Days
	Total Professional Fee 
	Total Travel Cost 
	Total Amount (All Inclusive Fee) 

	
	(A)
	(B)
	(C)
	(D)
	(E)
	(F = DxE)
	(G)
	(H = F+G)

	
1.
	• Baseline audit of existing data governance laws and policies. 
• Map existing child-focused data nodes (FAMCare, SISB, BHIS, BEMIS). 
• Evaluate dictionary gaps and workflows 
• Finalize work plan. 
	20 Nov 2026

	Domestic travel: Belize City – Belmopan, 2 trips of 1 day each 

	Click here
	7 days
	Click here
	Click here
	Click here

	2.
	• Draft Child-Sector DQAF aligned with UN/IMF/SIB standards. 
• Consolidate fragmented ministry data dictionaries into a unified metadata registry. 
• Design statistical validation procedures for data entry. 
• Technical reviews with the Policy and Planning Unit, MHDFSGA 
• Formulate Data Sharing Policy and inter-institutional MOUs. 
• Author Data Confidentiality and Privacy Standards Manual. 
• Develop Administrative Data Access Procedures. 
• Construct the Administrative Data Security Framework. 
	31 Dec 2026
	Domestic travel: Belize City – Belmopan, 8 trips of 1 day each 

	Click here
	25 days
	Click here
	Click here
	

	3.
	• Develop curriculum based on the finalized DQAF and governance manuals. 
• Execute capacity-building workshops for multi-sector personnel. 
• Administer competency tracking assessments. 
• Oversee initial pilot application of QA protocols. 
• Log data quality reviews and refine frameworks based on field feedback. 
• Transition frameworks to national counterparts and draft exit report. 
	 31 Jan 2027
	Domestic travel: Belize City – Belmopan, 5 trips of 1 day each 

	Click here
	15 days
	Click here
	Click here
	Click here 

	
	TOTAL AMOUNT – 47 days  
	
	
	Click here



Note: Shaded cells shall be filled by the Applicants.



Notes to financial offer:
1. Payment will be made on submission and acceptance of deliverables as stated above. UNICEF reserves the right to withhold payment in case the deliverables submitted are not up to the required standard or in case of delays in submitting the deliverables on the part of the consultant.
2. Air travel should be economy class using the most direct route.
3. No other fee would be paid or reimbursed other than the fee indicated in the financial proposal.
4. The consultant will work on own computer(s) and use own office resources and materials in the execution of this assignment, including personal email address(es) and phones. 
5. All pocket expenses including travel will be included in the specific lumpsum deliverables fees and paid as part of satisfactory completion of the deliverables. If the deliverables are not completed or achieved, these costs will not be paid separately.

PAYMENT TERMS: Net 30 days

Name of the Applicant: Click here
Signature of the Applicant: Click here 	
Address:  Click here
Contact no.:  Click here	
Email address:  Click here
Date: Click here
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