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TEMPLATE FOR FINANCIAL PROPOSAL

INDIVIDUAL CONSULTANT FOR WASH & Solar Construction Consultant

Currency of the proposal: USD

	S. No.
	Deliverables
	Deadline for completion of deliverable
	Details of Travel Required
	Professional Fee (Daily)


	Input Days
	Total Professional Fee 
	Total Travel Cost 
	Total Amount (All Inclusive Fee) 

	
	(A)
	(B)
	(C)
	(D)
	(E)
	(F = DxE)
	(G)
	(H = F+G)

	
1.
	Deliverable 1 - Inception and Technical Design Review: site verification, design review, Bills of Quantities, workplan and risk assessment.
& Mobilization Plan: contractor readiness, logistics plan, site preparation and coordination.

Inception and Technical Design Review 
Submit an inception report incorporating verified site information, review of designs and Bills of Quantities, implementation workplan, key technical risks and proposed mitigation measures & Mobilisation Plan 
Submit a mobilisation plan confirming contractor readiness, logistics arrangements, site preparation requirements, implementation sequencing, stakeholder& coordination arrangements
	15 January 2027 
	Do Not Fill
	Click here
	36
	Click here
	Do Not Fill
	Click here

	2.
	Deliverable 2 -  Monthly Supervision Report3 : progress, quality assurance checks, contractor performance, corrective actions and any required modifications.

Submit monthly  report documenting physical progress, quality assurance findings, contractor performance, implementation issues, corrective actions agreed and any recommended technical modifications
	Monthly deliverables
28 Feb
31 March
30 April
31 May
30 June 
31 July
31 August 
30 September 
	Do Not Fill
	Click here
	165
	Click here
	Do Not Fill
	

	3.
	Deliverable 3 - Final Phase Supervision Report: completion status, Bills of Quantities validation, defects tracking and certification support.

Submit a final-phase supervision report confirming completion status, validation of Bills of Quantities, outstanding defects and corrective measures, and technical inputs required for certification of completed works.
	31 October 2027 
	Do Not Fill
	Click here
	20 
	Click here
	Do Not Fill
	Click here 

	4.
	Deliverable 4 - Quality Assurance and Handover Report: final inspection, handover documents, operation and maintenance tools and lessons learned.
	30 November 2027 
	Do Not Fill
	Click here
	20

	Click here
	Do Not Fill
	

	5.
	Deliverable 5 - Final Report: implementation summary, coordination, capacity building and recommendations for operation and maintenance.
	31 December 2027 
	Do Not Fill
	Click here
	20
	Click here
	Do Not Fill
	

	
	TOTAL AMOUNT 
	
	
	Click here



Note: Shaded cells shall be filled by the Applicants.



Notes to financial offer:
1. Payment will be made on submission and acceptance of deliverables as stated above. UNICEF reserves the right to withhold payment in case the deliverables submitted are not up to the required standard or in case of delays in submitting the deliverables on the part of the consultant.
2. Air travel should be economy class using the most direct route.
3. No other fee would be paid or reimbursed other than the fee indicated in the financial proposal.
4. The consultant will work on own computer(s) and use own office resources and materials in the execution of this assignment, including personal email address(es) and phones. 
5. All pocket expenses including travel will be included in the specific lumpsum deliverables fees and paid as part of satisfactory completion of the deliverables. If the deliverables are not completed or achieved, these costs will not be paid separately.

PAYMENT TERMS: Net 30 days

Name of the Applicant: Click here
Signature of the Applicant: Click here 	
Address:  Click here
Contact no.:  Click here	
Email address:  Click here
Date: Click here
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