TEMPLATE FOR FINANCIAL PROPOSAL

INDIVIDUAL CONSULTANT FOR

Senior Public Finance and Refugee Inclusion Costing Consultant (International/National)

Currency of the proposal: USD
(ETB will be paid for Nationals)

| S. No. | Deliverables | Deadline for completion of deliverable | Details of Travel Required | Professional Fee (Daily) | Input Days | Total Professional Fee |  | Total Travel Cost |  | Total Amount (All Inclusive Fee) |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | (A) | (B) | (C) | (D) | (E) | (F = DxE) |  | (G) |  | (H = F+G) |  |
| 1. | Refined methodology; Sector and data availability assessment; Stakeholder mapping; Workplan; Interview guides; Facility costing templates; Consultation tools; Data-request templates. | 15.11.2026 | NA | Click here | Click here | Click here |  | NA |  | Click here |  |
| 2. | Three weeks (or 4 weeks depending on the number of refugee hosting areas to be selected for the study during the inception phase) of field research completed to assess the situation and multi-sector social service delivery gaps plus available data collection; Service delivery (plus management) and financing mapping; Unit costs; Incremental costs; Financing gaps; Delivery of practical workshops for jointly defining minimum standards/packages, costing assumptions, costing exercises and use of costing models (travel to Ethiopia required); Preliminary findings. | 31.01.2027 | Phase 1: 7 working days in Addis Ababa to meet with stakeholders; and discuss with partners to set the minimum standards/packages and yearly milestones by sector. 7 days (including travel time) each to visit 3 refugee hosting areas (i.e. 21 days in total) to Asayita (Afar Region), Kebribeyah (Somali Region), and a Refugee Hosting Area under the RRS Melkadida Branch Office (Somali Region)) to assess the situation and multi-sector social service delivery gaps plus available data collection. Phase 2: 5 working days in Addis Ababa for a workshop with partners for a consensus on costing assumptions and conducting costing exercises | Click here | Click here | Click here |  | Click here |  | Click here |  |
| 3. | Revised costing analysis; Cost-of-inaction analysis; Targeted cost-effectiveness analysis; one week visit in Addis to conduct validation workshop and agree with RRS on policy recommendation and framing of policy brief. | 31.04.2027 | 5 working days in Addis Ababa for a workshop on costing exercises with partners, as well as a validation workshop with stakeholders | Click here | Click here | Click here |  | Click here |  | Click here |  |
| 4. | Refugee inclusion investment case; Policy brief; PowerPoint slides, Validation workshop report; Replicable costing framework (reusable costing tools and guidance materials) and capacity-building completion note. | 30.06.2027 | NA | Click here | Click here | Click here |  | NA |  | Click here |  |
|  | TOTAL AMOUNT |  |  |  |  |  |  |  |  |  | Click here |  |

Note: Shaded cells shall be filled by the Applicants.

Notes to financial offer:

- Payment will be made on submission and acceptance of deliverables as stated above. UNICEF reserves the right to withhold payment in case the deliverables submitted are not up to the required standard or in case of delays in submitting the deliverables on the part of the consultant.

- Air travel should be economy class using the most direct route.

- No other fee would be paid or reimbursed other than the fee indicated in the financial proposal.

- The consultant will work on own computer(s) and use own office resources and materials in the execution of this assignment, including personal email address(es) and phones.

- All pocket expenses including travel will be included in the specific lumpsum deliverables fees and paid as part of satisfactory completion of the deliverables. If the deliverables are not completed or achieved, these costs will not be paid separately.

PAYMENT TERMS: Net 30 days

Name of the Applicant: Click here

Signature of the Applicant: Click here

Address:  Click here

Contact no.:  Click here

Email address:  Click here

Date: Click here