TEMPLATE FOR FINANCIAL PROPOSAL

INDIVIDUAL CONSULTANT FOR Consultancy for Technical Assistance to Strengthen Diversion, Probation and Alternative Measures for Children in the Turkish Child Justice System

Currency of the proposal: USD

| S. No. | Deliverables | Deadline for completion of deliverable | Details of Travel Required | Professional Fee (Daily) | Input Days | Total Professional Fee |  | Total Travel Cost |  | Total Amount (All Inclusive Fee) |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | (A) | (B) | (C) | (D) | (E) | (F = DxE) |  | (G) |  | (H = F+G) |  |
| 1. | Situation Analysis of the Child Bureaus of the Public Prosecutor’s Offices | 10 December 2026 | Meetings/consultations; Ankara and/or pilot provinces as required. | Click here | Click here | Click here |  | Click here |  | Click here |  |
| 2. | SOPs Manual for Child Bureaus of Public Prosecutor’s Offices | 29 January 2027 | Remote/desk-based. | Click here | Click here | Click here |  | Click here |  | Click here |  |
| 3. | Conducting Consultation with Stakeholders on SOPs Manual for Child Bureaus of Public Prosecutor’s Offices | 26 February 2027 | Stakeholder consultation; Ankara and/or pilot provinces. | Click here | Click here | Click here |  | Click here |  | Click here |  |
| 4. | Conducting Consultation with TF on SOPs Manual for Child Bureaus of Public Prosecutor’s Offices | 16 April 2027 | Task Force consultation; remote. | Click here | Click here | Click here |  | Click here |  | Click here |  |
| 5. | Situation Analysis of the Child Bureaus of the Public Prosecutor’s Offices | 10 December 2026 | Remote– multi-agency consultations; Ankara | Click here | Click here | Click here |  | Click here |  | Click here |  |
| 6. | Conducting Initial Consultation on Guidelines and Specialized Programmes | 10 December 2026 | Remote/desk-based. |  |  |  |  |  |  |  |  |
|  | Assessment Guidelines for Caseworkers | 29 January 2027 | Remote/desk-based. |  |  |  |  |  |  |  |  |
| 7. | Diversion, Probation and Alternative Measures Implementation SOPs | 29 January 2027 | Remote/desk-based. |  |  |  |  |  |  |  |  |
| 8. | Specialized Reintegration, Rehabilitation and Restitution Sub-Programs | 29 January 2027 | Participation during the A-3 Ankara mission; consultations with other provinces may be conducted remotely. No separate trip. |  |  |  |  |  |  |  |  |
| 9. | Conducting Follow-up Consultations on Guidelines and Sub-Programmes | 26 February 2027 | Remote. Task Force consultation.. |  |  |  |  |  |  |  |  |
| 10. | Conducting Consultation with TF on Guidelines and Sub-Programmes | 16 April 2027 | Remote/desk-based. |  |  |  |  |  |  |  |  |
| 11. | Final Package of Assessment Guidelines, Manuals, SOPs for the Implementation of the Diversion and Alternative Measures Programs | 11 June 2027 | Remote/desk-based. |  |  |  |  |  |  |  |  |
| 12. | Comprehensive Modular Training Curriculum | 16 July 2027 | Remote/desk-based; production support as required. |  |  |  |  |  |  |  |  |
| 13. | Scenario-Based Video Production Master Scripts | 16 July 2027 | Two grouped missions to selected pilot provinces, totalling 5 working days on site; to Antalya, Erzurum, Istanbul, Şanlıurfa and Tokat; exact trips/days TBC. |  |  |  |  |  |  |  |  |
| 14. | Training Delivery in 5 Provinces for 250 Professionals | 30 September 2027 | Field visits to the 5 pilot provinces; exact trip schedule/days. Working days total: approximately 15 days on site and 5 days for travel and movement between locations |  |  |  |  |  |  |  |  |
| 15. | Conducting Field Visits during Pilot Implementation | 31 January 2028 | – pilot oversight may require field travel to the 5 pilot provinces. |  |  |  |  |  |  |  |  |
| 16. | Overseeing Pilot Implementation | 26 May 2028 | Remote/desk-based. |  |  |  |  |  |  |  |  |
| 17. | Assessment Report of Pilot Implementation | 9 June 2028 | Remote/desk-based. |  |  |  |  |  |  |  |  |
| 18. | Final Package of SOPs, Assessment Guidelines, Sub-Program Manuals, training program and e-learning modules for National Implementation | 23 June 2028 | ToT involving professionals from 5 pilot provinces; location/trips/days to be confirmed. One mission to the ToT venue in Türkiye, 2 working days on site |  |  |  |  |  |  |  |  |
| 19. | ToT Program Delivery for National Diversion Implementation for 60 Professionals | 30 June 2028 | Remote/desk-based. |  |  |  |  |  |  |  |  |
| 20. | Nationwide Training Rollout Strategy for Diversion Implementation | 10 July 2028 | Meetings/consultations; Ankara and/or pilot provinces as required. |  |  |  |  |  |  |  |  |
|  | TOTAL AMOUNT 135 days |  |  |  |  |  |  |  |  |  | Click here |  |

Note: Shaded cells shall be filled by the Applicants.

Notes to financial offer:

- Payment will be made on submission and acceptance of deliverables as stated above. UNICEF reserves the right to withhold payment in case the deliverables submitted are not up to the required standard or in case of delays in submitting the deliverables on the part of the consultant.

- Air travel should be economy class using the most direct route.

- No other fee would be paid or reimbursed other than the fee indicated in the financial proposal.

- The consultant will work on own computer(s) and use own office resources and materials in the execution of this assignment, including personal email address(es) and phones.

- All pocket expenses including travel will be included in the specific lumpsum deliverables fees and paid as part of satisfactory completion of the deliverables. If the deliverables are not completed or achieved, these costs will not be paid separately.

PAYMENT TERMS: Net 30 days

Name of the Applicant: Click here

Signature of the Applicant: Click here

Address:  Click here

Contact no.:  Click here

Email address:  Click here

Date: Click here