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TEMPLATE FOR FINANCIAL PROPOSAL

INDIVIDUAL CONSULTANT FOR National Consultant for Hygiene Programming, Evidence Generation and Knowledge Management

Currency of the proposal BDT

	S. No.
	Deliverables
	Deadline for completion of deliverable
	Details of Travel Required
	Professional Fee (Daily)


	Input Days
	Total Professional Fee 
	Total Travel Cost 
	Total Amount (All Inclusive Fee) 

	
	(A)
	(B)
	(C)
	(D)
	(E)
	(F = DxE)
	(G)
	(H = F+G)

	
1.
	Inception report and consolidated workplan approved by UNICEF, including methodology, activity schedule, stakeholder coordination arrangements, deliverable calendar, travel plan, key risks and mitigation measures
	
31 January 2027
	
	Click here
	Click here
	Click here
	Click here
	Click here

	2.
	Draft package of campaign SBC materials developed and technically reviewed through at least three documented stakeholder consultations, with a consultation summary and feedback matrix submitted to UNICEF
	28 February 2027
	2 field trips for 6 days to Gazipur
	Click here
	Click here
	Click here
	Click here
	

	3.
	District and school selection criteria, proposed list of participating schools, stakeholder roles, implementation schedule and monitoring arrangements finalized and documented, with evidence of endorsement by the relevant authorities
	 30 April 2027
	1 field trip for 4 days to Khulna

	Click here
	Click here
	Click here
	Click here
	Click here 

	4.
	 Final MHM Campaign SBC package submitted following incorporation of consolidated technical feedback, accompanied by response matrix and documented evidence of review/endorsement by the designated government coordination and approval mechanism
	31 May 2027
	1 field trip for 2 days to Gazipur

	Click here
	Click here
	Click here
	Click here
	

	5.
	Two context-specific hygiene concept notes finalized, each including a problem statement, evidence base, target population, proposed approach, theory of change implementation pathway, partnership options, indicative budget and key risks
	30 July 2027
	
	Click here
	Click here
	Click here
	Click here
	

	6.
	Campaign launched and initial implementation completed in approximately 100 selected schools, with a campaign implementation report documenting school coverage, participant reach, delivery channels, monitoring findings, implementation challenges, corrective actions and supporting evidence.
	30 September
2027
	4 field trips for 12 days to Cumilla, Khulna and Gazipur
	
	
	
	
	

	7.
	Assessment framework finalized and applied to one selected hygiene solution, with an assessment report covering relevance, user acceptability, inclusion, operational feasibility, indicative cost, sustainability and recommendation for adaptation or potential scale up
	30 October 2027
	2 field trips, 6 days to Cox’s Bazar and Barisal
	
	
	
	
	

	8.
	At least five finalized communication and knowledge products produced and disseminated through UNICEF communication channels and relevant platforms. Products may include humaninterest stories, briefs, infographics, presentations, web articles or technical summaries
	15 December 2027
	2 field trips, 6 days to Khulna and Chittagong
	
	
	
	
	

	9.
	Final campaign documentation and learning package approved by UNICEF, comprising: (i) implementation narrative; (ii) monitoring results; (iii) stakeholder and participant feedback; (iv) lessons learned and good practices; (v) documented challenges and mitigation measures; and (vi) recommendations and roadmap for institutionalization, replication and potential scale-up
	20 December 2027

	2 field trips for 6 days to Khulna and Cumilla
	
	
	
	
	

	10.
	Three analytical products finalized and approved by UNICEF, selected at inception from the agreed list of priority products. Each product will include documented data sources, methodology, key findings, limitations, visualizations and actionable programme or policy recommendations.
	15 December 2027
	2 field trips for 6 days to Khulna and Bagerhat
	
	
	
	
	

	
	TOTAL AMOUNT 
	
	
	Click here



Note: Shaded cells shall be filled by the Applicants.



Notes to financial offer:
1. Payment will be made on submission and acceptance of deliverables as stated above. UNICEF reserves the right to withhold payment in case the deliverables submitted are not up to the required standard or in case of delays in submitting the deliverables on the part of the consultant.
2. Air travel should be economy class using the most direct route.
3. No other fee would be paid or reimbursed other than the fee indicated in the financial proposal.
4. The consultant will work on own computer(s) and use own office resources and materials in the execution of this assignment, including personal email address(es) and phones. 
5. All pocket expenses including travel will be included in the specific lumpsum deliverables fees and paid as part of satisfactory completion of the deliverables. If the deliverables are not completed or achieved, these costs will not be paid separately.

PAYMENT TERMS: Net 30 days

Name of the Applicant: Click here
Signature of the Applicant: Click here 	
Address:  Click here
Contact no.:  Click here	
Email address:  Click here
Date: Click here
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