UNICEF - Internal use only

UNICEF - Internal use only

[image: ]                                                                         Human ResourcesUnited Nations Children’s Fund 
 







TEMPLATE FOR FINANCIAL PROPOSAL

INDIVIDUAL CONSULTANT FOR Construction Engineer Consultant- Teraina and Tabuaeran

Currency of the proposal: USD

	S. No.
	Deliverables
	Deadline for completion of deliverable
	Details of Travel Required
	Professional Fee (Daily)


	Input Days
	Total Professional Fee 
	Total Travel Cost 
	Total Amount (All Inclusive Fee) 

	
	(A)
	(B)
	(C)
	(D)
	(E)
	(F = DxE)
	(G)
	(H = F+G)

	
1.
	Inception, technical review and mobilisation package: approved work plan; stakeholder and contractor coordination arrangements; consolidated site status and risk register; review of drawings, specifications and bills of quantities; permit and endorsement tracker; kick-off meetings; verification of site possession, contractor mobilisation, materials, health and safety plans, quality plans, programme, inspection and hold points. (20 days)
	31 Dec 2026
	NA
	Click here
	Click here
	Click here
	Click here
	Click here

	2.
	January field monitoring and progress report submitted to the Ministry and UNICEF, covering physical and financial progress, quality, safety, risks, photographs, decisions required, agreed actions and updated construction tracker. (20 days)
	31 Jan 2027
	NA
	Click here
	Click here
	Click here
	Click here
	

	3.
	February field monitoring and technical supervision report, including site inspections, supervision-report review, material and test-result review, milestone status, technical obstacles, corrective actions, expenditure, variations, health and safety and updated action trackers. (20 days)
	28 Feb 2027
	
NA
	Click here
	Click here
	Click here
	Click here
	Click here 

	4.
	March construction and contract-administration report: verified quantities and quality; payment certificate and variation review; updated construction records; forecast to completion; and advice on delays, amendments, extensions or liquidated damages where applicable. (20 days)
	31 Mar 2027
	
NA
	Click here
	Click here
	Click here
	Click here
	

	5.
	April quality-assurance and completion-readiness report: joint monitoring with government services; outstanding works and defect lists; testing, training and handover requirements; operation and maintenance documentation status; and completion plan for all 11 facilities. (20 days)
	30 Apr 2027
	NA
	Click here
	Click here
	Click here
	Click here
	

	6.
	May commissioning and handover report: participation in partial/substantial reception; verification of testing, training and defect correction; review of as-built drawings, operation and maintenance documents, warranties, certificates and handover records; updated payment and close-out status. (20 days)
	31 May 2027
	NA
	
	
	
	
	

	7.
	Final completion and contract close-out package: final inspection/reception; verification of defect correction; final payment recommendations as authorised; contract performance evaluations; complete archived contract file; final construction tracker; and completion report with lessons learned and good practices. Target: construction completed in six schools and five healthcare facilities in Teraina and Tabuaeran. (20 days)
	30 Jun 2027
	NA
	
	
	
	
	

	
	TOTAL AMOUNT 
	
	
	Click here



Note: Shaded cells shall be filled by the Applicants.



Notes to financial offer:
1. Payment will be made on submission and acceptance of deliverables as stated above. UNICEF reserves the right to withhold payment in case the deliverables submitted are not up to the required standard or in case of delays in submitting the deliverables on the part of the consultant.
2. Air travel should be economy class using the most direct route.
3. No other fee would be paid or reimbursed other than the fee indicated in the financial proposal.
4. The consultant will work on own computer(s) and use own office resources and materials in the execution of this assignment, including personal email address(es) and phones. 
5. All pocket expenses including travel will be included in the specific lumpsum deliverables fees and paid as part of satisfactory completion of the deliverables. If the deliverables are not completed or achieved, these costs will not be paid separately.

PAYMENT TERMS: Net 30 days

Name of the Applicant: Click here
Signature of the Applicant: Click here 	
Address:  Click here
Contact no.:  Click here	
Email address:  Click here
Date: Click here
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