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TEMPLATE FOR FINANCIAL PROPOSAL

INDIVIDUAL CONSULTANT FOR Program Coordinating Consultant – EdTech for Improving Foundational Learning

Currency of the proposal: NPR

	S. No.
	Deliverables
	Deadline for completion of deliverable
	Details of Travel Required
	Professional Fee (Daily)


	Input Days
	Total Professional Fee 
	Total Travel Cost 
	Total Amount (All Inclusive Fee) 

	
	(A)
	(B)
	(C)
	(D)
	(E)
	(F = DxE)
	(G)
	(H = F+G)

	
1.
	Inception report including detailed workplan, methodology, monitoring framework, implementation plan of the EdTech initiative, stakeholder mapping, alignment with government systems.
	28 February 2027
	NA
	Click here
	Click here
	Click here
	DO NOT FILL
	Click here

	2.
	· Partnerships set up
· Implementation in place
· Digital labs set up in schools
Schools identified and action plans in place 
	15th April 2027
	Three days each to Lumbini and Madhesh  
	Click here
	Click here
	Click here
	Click here
	

	3.
	· Monitoring system developed and implemented
· Technical support provided to teachers and schools; resource materials developed/adapted; documentation of effective curriculum implementation practices and challenges.
· Edtech labs smoothly running and being used in schools 
· Teachers trained on using EdTech to improve foundational learning 
· Reports completed for donor reporting
· Learning from the implementation documented, risks identified and mitigation measures in place
· Mid-term review report including implementation progress, risks, lessons learned and recommendations



	10th July 2027
	Five days each to Lumbini and Madhesh  
	Click here
	Click here
	Click here
	Click here
	Click here 

	4.
	· Report of progress, follow-up support provided, further needs identified and plans in place 
· Support virtual Community of Practice sessions 
· Technical support provided to teachers and schools; resource materials developed/adapted; documentation of effective curriculum implementation practices and challenges.
· Reports completing for donor reporting
· Work closely with field office and academic coordinators to ensure effective implementation of Edtech initiatives 


	30th Oct 2027
	Five days each to Lumbini and Madhesh  
	Click here
	Click here
	Click here
	DO NOT FILL
	

	5.
	· Case studies and evidence of learnings 
Final report with recommendations
	30th Dec 2027
	NA
	Click here
	Click here
	Click here
	DO NOT FILL
	

	
	TOTAL AMOUNT 
	
	
	Click here



Note: Shaded cells shall be filled by the Applicants.



Notes to financial offer:
1. Payment will be made on submission and acceptance of deliverables as stated above. UNICEF reserves the right to withhold payment in case the deliverables submitted are not up to the required standard or in case of delays in submitting the deliverables on the part of the consultant.
2. Air travel should be economy class using the most direct route.
3. No other fee would be paid or reimbursed other than the fee indicated in the financial proposal.
4. The consultant will work on own computer(s) and use own office resources and materials in the execution of this assignment, including personal email address(es) and phones. 
5. All pocket expenses including travel will be included in the specific lumpsum deliverables fees and paid as part of satisfactory completion of the deliverables. If the deliverables are not completed or achieved, these costs will not be paid separately.

PAYMENT TERMS: Net 30 days

Name of the Applicant: Click here
Signature of the Applicant: Click here 	
Address:  Click here
Contact no.:  Click here	
Email address:  Click here
Date: Click here
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