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TEMPLATE FOR FINANCIAL PROPOSAL

INDIVIDUAL CONSULTANT FOR Maternal Nutrition, Food Fortification and broader Micronutrients Agenda)

Currency of the proposal: PHP

	S. No.
	Deliverables
	Deadline for completion of deliverable
	Details of Travel Required
	Professional Fee (Daily)


	Input Days
	Total Professional Fee 
	Total Travel Cost 
	Total Amount (All Inclusive Fee) 

	
	(A)
	(B)
	(C)
	(D)
	(E)
	(F = DxE)
	(G)
	(H = F+G)

	
1.
	
An approved inception report and detailed workplan that clearly define the scope of work, priority activities, expected results, key stakeholders, coordination mechanisms, risks and mitigation measures, and milestones for all workstreams.
	
December 31, 2026.
	
	Click here
	Click here
	Click here
	Click here
	Click here

	2.
	A progress report which includes an implementation tracking mechanism with documented technical inputs, coordination actions, implementation updates, identified bottlenecks and risks, and actionable recommendations to accelerate progress against
agreed priorities and milestone
	January 31, 2027
	
	Click here
	Click here
	Click here
	Click here
	

	3.
	A progress report which includes a validated IFA-toMMS Transition Roadmap that defines strategic priorities, implementation milestones, institutional responsibilities, resource and operational requirements, partner contributions, monitoring mechanisms, key risks and mitigation measures, and sustainability actions.
	 February 28, 2027
	

	Click here
	Click here
	Click here
	Click here
	Click here 

	4.
	 A progress report which includes an implementation tracking mechanism with documented technical inputs, coordination actions, implementation updates, identified bottlenecks and risks, and actionable recommendations to accelerate progress against agreed priorities and milestone
	March 31, 2027
	

	Click here
	Click here
	Click here
	Click here
	

	5.
	A progress report that elaborates the technical assistance provided supported through regular meetings and technical discussions, with an updated partner mapping/tracking mechanism, documented commitments and action points, and evidence of improved alignment and complementarity of partner support with DOH priorities.
	April 30, 2027
	
	
	
	
	
	

	6.
	A progress report that documents implementation and coordination support, including progress tracking against agreed priorities, technical assistance, stakeholder engagement, monitoring findings, identified implementation gaps, and recommendations to strengthen programme performance and sustainability
	May 31, 2027
	
	Click here
	Click here
	Click here
	Click here
	

	7.
	A progress report which includes an implementation tracking mechanism with documented technical inputs, coordination actions, implementation updates identified bottlenecks and risks, and actionable recommendations to accelerate progress against agreed priorities and milestone
	June 30, 2027
	
	
	
	
	
	

	8.
	A progress report that documents the assessment and recommendations for strengthening food fortification monitoring and regulatory systems, including agreed technical inputs, coordination mechanisms with FDA and relevant agencies, review of monitoring tools and reporting arrangements, and actionable recommendations to improve compliance, quality assurance, and data use.
	July 31, 2027
	
	
	
	
	
	

	9.
	A progress report which includes an implementation tracking mechanism with documented technical inputs, coordination actions, implementation updates, identified bottlenecks and risks, and actionable recommendations to accelerate progress against agreed priorities and milestone
	August 31, 2027
	
	
	
	
	
	

	10.
	A progress report which includes an implementation tracking mechanism with documented technical inputs, coordination actions, implementation updates, identified bottlenecks and risks, and actionable recommendations to accelerate progress against agreed priorities and milestone
	September 30, 2027
	
	
	
	
	
	

	  11.
	A progress report which
includes an implementation
tracking mechanism with
documented technical inputs,
coordination actions,
implementation updates,
identified bottlenecks and
risks, and actionable
recommendations to
accelerate progress against
agreed priorities and
milestone
	October 31, 2027
	
	
	
	
	
	

	12.
	A final consultancy report documenting achievements against agreed deliverables and milestones, key technical and coordination contributions, implementation challenges and responses, institutional strengthening results, lessons learned, sustainability considerations, and prioritized recommendations and actions for continued support to NNC and DOH.
	November 15, 2027
	
	
	
	
	
	

	
	
	
	
	
	
	
	
	

	
	TOTAL AMOUNT 
	
	
	Click here



Note: Shaded cells shall be filled by the Applicants.



Notes to financial offer:
1. Payment will be made on submission and acceptance of deliverables as stated above. UNICEF reserves the right to withhold payment in case the deliverables submitted are not up to the required standard or in case of delays in submitting the deliverables on the part of the consultant.
2. Air travel should be economy class using the most direct route.
3. No other fee would be paid or reimbursed other than the fee indicated in the financial proposal.
4. The consultant will work on own computer(s) and use own office resources and materials in the execution of this assignment, including personal email address(es) and phones. 
5. All pocket expenses including travel will be included in the specific lumpsum deliverables fees and paid as part of satisfactory completion of the deliverables. If the deliverables are not completed or achieved, these costs will not be paid separately.

PAYMENT TERMS: Net 30 days

Name of the Applicant: Click here
Signature of the Applicant: Click here 	
Address:  Click here
Contact no.:  Click here	
Email address:  Click here
Date: Click here
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