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TEMPLATE FOR FINANCIAL PROPOSAL
INDIVIDUAL CONSULTANT FOR   National Consultant – 
Integrated Specimen Referral System (iSRS) Coordination 

Currency of the proposal: LAK

	S. No.
	Deliverables
	Deadline for completion of deliverable
	Details of Travel Required
	Professional Fee (Daily)


	Input Days
	Total Professional Fee 
	Total Travel Cost 
	Total Amount (All Inclusive Fee) 

	
	(A)
	(B)
	(C)
	(D)
	(E)
	(F = DxE)
	(G)
	(H = F+G)

	
1.
	Inception and iSRS coordination plan
	29/01/2027
	N/A
	Click here
	Click here
	Click here
	Click here
	Click here

	2.
	iSRS framework, SOPs and tools
	26/02/2027
	N/A
	Click here
	Click here
	Click here
	Click here
	

	3.
	National Training of Trainers
	31/03/2027
	N/A

	Click here
	Click here
	Click here
	Click here
	Click here 

	4.
	 Cascade launch and transport arrangements
	30/04/2027
	1 trip to 1–2 scale-up provinces, approx. 3 days
	Click here
	Click here
	Click here
	Click here
	

	5.
	Cascade completion and first supportive supervision
	31/05/2027
	1 trip to 1–2 scale-up provinces, approx. 3 days
	Click here
	Click here
	Click here
	Click here
	

	6.
	Year-1 target verification
	30/06/2027
	1 trip to 1–2 scale-up provinces, approx. 3 days
	Click here
	Click here
	Click here
	Click here
	

	7.
	Annual review and Year-2 planning
	30/07/2027
	N/A

	Click here
	Click here
	Click here
	Click here
	

	8.
	iSRS performance monitoring
	31/08/2027
	N/A

	Click here
	Click here
	Click here
	Click here
	

	9.
	Second supportive supervision
	30/09/2027
	1 trip to 1–2 scale-up provinces, approx. 3 days
	Click here
	Click here
	Click here
	Click here
	

	10.
	Refresher training design
	29/10/2027
	N/A

	Click here
	Click here
	Click here
	Click here
	

	11.
	Outbreak readiness and quarterly monitoring
	30/11/2027
	N/A

	Click here
	Click here
	Click here
	Click here
	

	12.
	Final report and handover
	24/12/2027
	N/A
	Click here
	Click here
	Click here
	Click here
	

	
	TOTAL AMOUNT 
	
	
	Click here



Note: Shaded cells shall be filled by the Applicants.



Notes to financial offer:
1. Payment will be made on submission and acceptance of deliverables as stated above. UNICEF reserves the right to withhold payment in case the deliverables submitted are not up to the required standard or in case of delays in submitting the deliverables on the part of the consultant.
2. Air travel should be economy class using the most direct route.
3. No other fee would be paid or reimbursed other than the fee indicated in the financial proposal.
4. The consultant will work on own computer(s) and use own office resources and materials in the execution of this assignment, including personal email address(es) and phones. 
5. All pocket expenses including travel will be included in the specific lumpsum deliverables fees and paid as part of satisfactory completion of the deliverables. If the deliverables are not completed or achieved, these costs will not be paid separately.

PAYMENT TERMS: Net 30 days

Name of the Applicant: Click here
Signature of the Applicant: Click here 	
Address:  Click here
Contact no.:  Click here	
Email address:  Click here
Date: Click here
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