TEMPLATE FOR FINANCIAL PROPOSAL

INDIVIDUAL CONSULTANT FOR Sanitation Finance Consultant

Currency of the proposal: USD – for internationals /NGN – for nationals

| S. No. | Deliverables | Deadline for completion of deliverable | Details of Travel Required | Professional Fee (Daily) | Input Days | Total Professional Fee | Total Travel Cost | Total Amount (All Inclusive Fee) |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | (A) | (B) | (C) | (D) | (E) | (F = DxE) | (G) | (H = F+G) |
| 1. | Inception report | 30 November 2026 | NA | Click here | Click here | Click here | NA | Click here |
| 2. | Stakeholder and institutional map (with named focal points and entry points) | 10 December 2026 | Abuja (if not based there) – 1 trip x 3 days Lagos (if not based there) – 1 trip x 3 days | Click here | Click here | Click here | Click here | Click here |
| 3. | Consolidated source pack (studies, datasets, government documents) indexed, and written comments on the market assessment team inception report. | 15 December 2026 | NA | Click here | Click here | Click here | NA | Click here |
| 4. | Financial institution mapping note, with a shortlist recommendation and a note on the role informal savings groups could play as a distribution and repayment channel. | 15 January 2027 | NA | Click here | Click here | Click here | NA | Click here |
| 5. | Consolidated comments of the draft market assessment, with a written assessment of remaining data gaps. | 15 February 2027 | NA | Click here | Click here | Click here | NA | Click here |
| 6. | Drafting inputs to the updated Nigeria SPF Country Context Report and to the Nigeria SPF concept note. | 15 March 2027 | NA | Click here | Click here | Click here | NA | Click here |  |
| 7. | Consolidated report with comments on data collection tools and market assessment and business model for bankable models (FSTP & PPP for public places) | 30 April 2027 | NA | Click here | Click here | Click here | NA | Click here |  |
| 8. | Report that provides review of the financing model (demand estimates, guarantee-sizing inputs, scenarios), and inputs to the TA budget and implementation plan. | 30 June 2027 | Abuja (if not based there) – 1 trip x 3 days Lagos (if not based there) – 1 trip x 3 days | Click here | Click here | Click here | Click here | Click here |  |
| 9. | Final Steering committee composition, terms of reference, and minutes of first two meetings convened | 15 September 2027 | Abuja (if not based there) – 2 trips x 3 days each | Click here | Click here | Click here | Click here | Click here |  |
| 10. | National and one state level framework for targeted subsidies developing, including implementation guide | 31 July 2027 | Ondo (if not based there) – 1 trip x 3 days | Click here | Click here | Click here | Click here | Click here |  |
| 11. | Written comments on four concept notes and proposals reviewed | 31 August 2027 | Abuja (if not based there) – 1 trip x 3 days | Click here | Click here | Click here | Click here | Click here |  |
| 12. | Report on technical assistance provided to development bank projects in at least one state | 30 September 2027 | Ondo (if not based there) – 2 trips x 3 days each | Click here | Click here | Click here | Click here | Click here |  |
| 13. | Consolidated meeting minutes with follow-up actions | 31 October 2027 | Abuja (if not based there) – 1 trip x 3 days Lagos (if not based there) – 1 trip x 3 days | Click here | Click here | Click here | Click here | Click here |  |
| 14. | Two knowledge products of progress and lessons learnt for the development of a bankable model (one for PPPs and one for FSM) | 10 November 2027 | Bauchi state (if not based there) – 2 trips x 5 days each | Click here | Click here | Click here | Click here | Click here |  |
| 15. | End-of-assignment report (max 10 pages) and handover pack: contact list, document library and updated SPF Project Management tool. | 10 November 2027 | NA | Click here | Click here | Click here | NA | Click here |  |
|  | TOTAL AMOUNT |  |  |  |  |  |  | Click here |  |

Note: Shaded cells shall be filled by the Applicants.

Notes to financial offer:

- Payment will be made on submission and acceptance of deliverables as stated above. UNICEF reserves the right to withhold payment in case the deliverables submitted are not up to the required standard or in case of delays in submitting the deliverables on the part of the consultant.

- Air travel should be economy class using the most direct route.

- No other fee would be paid or reimbursed other than the fee indicated in the financial proposal.

- The consultant will work on own computer(s) and use own office resources and materials in the execution of this assignment, including personal email address(es) and phones.

- All pocket expenses including travel will be included in the specific lumpsum deliverables fees and paid as part of satisfactory completion of the deliverables. If the deliverables are not completed or achieved, these costs will not be paid separately.

PAYMENT TERMS: Net 30 days

Name of the Applicant: Click here

Signature of the Applicant: Click here

Address:  Click here

Contact no.:  Click here

Email address:  Click here

Date: Click here