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TEMPLATE FOR FINANCIAL PROPOSAL

INDIVIDUAL CONSULTANT FOR National Consultant for PCRD and Pandemic Fund Projects

Currency of the proposal:MNT

	S. No.
	Deliverables
	Deadline for completion of deliverable
	Details of Travel Required
	Professional Fee (Daily)


	Input Days
	Total Professional Fee 
	Total Travel Cost 
	Total Amount (All Inclusive Fee) 

	
	(A)
	(B)
	(C)
	(D)
	(E)
	(F = DxE)
	(G)
	(H = F+G)

	
1.
	1. Accepted inception report covering both projects, with a documented desk review and baseline status; separate prioritized workplans, results and risk/action trackers, stakeholder map, reporting calendar, monitoring methodology, and written record of supervisor-agreed revisions. (22 days)
	30 Dec 2026

	NA
	Click here
	Click here
	Click here
	Click here
	Click here

	2.
	2. Accepted initial implementation progress report: distinct PCRD/Pandemic Fund progress summaries; logs of technical inputs, reviewed materials and consultations; first data quality/monitoring findings, bottleneck assessment, updated risk and results trackers, corrective-action plan for months 4–6, and reporting inputs due in period. (44 days)
	28 Feb 2027
	NA
	Click here
	Click here
	Click here
	Click here
	

	3.
	3. Accepted implementation and capacity-strengthening package: separate project target/indicator reviews, field and data-quality findings, analyses of UNICEF-validated implementation/expenditure information, revised technical materials and trackers, training/mentorship resources, delivery and participant feedback records, and reporting inputs due. (66 days)
	 30 May 2027
	NA

	Click here
	Click here
	Click here
	Click here
	Click here 

	4.
	 4. Accepted consolidated progress and corrective-action report for both projects: progress since month-6 review; documented closure/status of field and training recommendations; updated verified results, expenditure and risk trackers; remaining gaps, agreed corrective actions and responsible parties, donor inputs due, and draft sustainability/completion plan. (66 days)
	30 Aug 2027
	NA

	Click here
	Click here
	Click here
	Click here
	

	5.
	5. Accepted final results and handover package: separate evidence-backed project results and donor inputs; lessons, sustainability actions and unresolved commitments; complete indexed editable repository, final consultancy report, responsibilities register and records of agreed counterpart knowledge-transfer sessions. (66 days)
	30 Nov 2027
	NA
	Click here
	Click here
	Click here
	Click here
	

	
	TOTAL AMOUNT 
	
	
	Click here



Note: Shaded cells shall be filled by the Applicants.



Notes to financial offer:
1. Payment will be made on submission and acceptance of deliverables as stated above. UNICEF reserves the right to withhold payment in case the deliverables submitted are not up to the required standard or in case of delays in submitting the deliverables on the part of the consultant.
2. Air travel should be economy class using the most direct route.
3. No other fee would be paid or reimbursed other than the fee indicated in the financial proposal.
4. The consultant will work on own computer(s) and use own office resources and materials in the execution of this assignment, including personal email address(es) and phones. 
5. All pocket expenses including travel will be included in the specific lumpsum deliverables fees and paid as part of satisfactory completion of the deliverables. If the deliverables are not completed or achieved, these costs will not be paid separately.

PAYMENT TERMS: Net 30 days

Name of the Applicant: Click here
Signature of the Applicant: Click here 	
Address:  Click here
Contact no.:  Click here	
Email address:  Click here
Date: Click here
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