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TEMPLATE FOR FINANCIAL PROPOSAL

INDIVIDUAL CONSULTANT FOR Public Partnerships Consultancy 

Currency of the proposal: USD

	S. No.
	Deliverables
	Deadline for completion of deliverable
	Details of Travel Required
	Professional Fee (Daily)


	Input Days
	Total Professional Fee 
	Total Travel Cost 
	Total Amount (All Inclusive Fee) 

	
	(A)
	(B)
	(C)
	(D)
	(E)
	(F = DxE)
	(G)
	(H = F+G)

	
1.
	Deliverable 1 - Monthly progress report covering all five workstreams (activities completed, outputs shared, issues), plus: [WS1] Begin donor / opportunity analysis and Country Office intelligence support for Q1 [WS2] Start SharePoint audit [WS2] 1 Knowledge management plan produced (structure, naming, access, refresh schedule) [WS4] Start regional bodies mapping and engagement plan
	31 January 2027
	
	Click here
	Click here
	Click here
	Click here
	Click here to add text or click the + sign to add more rows

	2.
	Deliverable 2 -  Monthly progress report covering all five workstreams (activities completed, outputs shared, issues), plus: [WS2] 1 Donor or partner profile is developed [WS4] 1 Regional bodies mapping (priorities, focal points, ongoing and planned work, entry points for UNICEF) and 1 engagement plan are developed [WS2] SharePoint audit completed

	28 February 2027
	
	Click here
	Click here
	Click here
	Click here
	

	3.
	Deliverable 3 - Monthly progress report covering all five workstreams (activities completed, outputs shared, issues), plus: [WS1] Q1 delivery: 2 donor / opportunity analysis, proposals, concept notes or donor reports, and Country Office intelligence support [WS2, WS3] Q1 partnerships briefing/material or analysis product is developed [WS2] Q1 update of donor profiles, pipeline and trackers is made [WS5] 1 PPP prospect profile (Start PPP opportunity 1)
	 31 March 2027
	

	Click here
	Click here
	Click here
	Click here
	Click here to add text or click the + sign to add more rows

	4.
	Deliverable 4 - Monthly progress report covering all five workstreams (activities completed, outputs shared, issues), plus: [WS5] 1 PPP engagement pathway overview (PPP opportunity 1) [WS4] Analysis note #1 on regional bodies [WS1] Begin donor / opportunity analysis and Country Office intelligence support for Q2
	30 April 2027
	

	Click here
	Click here
	Click here
	Click here
	

	5.
	Deliverable 5 - Monthly progress report covering all five workstreams (activities completed, outputs shared, issues), plus: [WS2] At least 1 Donor or partner profile is developed [WS2] Documented Country Office support [WS5] 1 PPP proposal / concept note input (PPP opportunity 1)
	31 May 2027
	
	Click here
	Click here
	Click here
	Click here
	

	
	Deliverable 6 - Monthly progress report covering all five workstreams (activities completed, outputs shared, issues), plus: [WS1] Q2 delivery: At least 1 donor / resource mobilization opportunity analysis document is developed and Country Office intelligence support is provided [WS2] Q2 update of donor profiles, pipelines and trackers [WS2, 3] Regional newsletter #1 [WS2] 1 briefing note/materials or analysis product (Q2)
	30 June 2027
	
	
	
	
	
	

	
	Deliverable 7 - Monthly progress report covering all five workstreams (activities completed, outputs shared, issues), plus: [WS4] Relationship updates with regional bodies [WS1] Begin donor / opportunity analysis and Country Office intelligence support for Q3
	31 July 2027
	
	
	
	
	
	

	
	Deliverable 8 - Monthly progress report covering all five workstreams (activities completed, outputs shared, issues), plus: [WS2] At least 1 Donor or partner profile is developed [WS2] Documented Country Office support [WS5] Start PPP opportunity 2: 1 prospect profile
	31 August 2027
	
	
	
	
	
	

	
	Deliverable 9 - Monthly progress report covering all five workstreams (activities completed, outputs shared, issues), plus: [WS1] Q3 delivery: At least 1 Donor / opportunity analysis, proposals, concept notes or donor reports, and Country Office intelligence support [WS2, WS3] At least 1 briefing or analysis product is developed (Q3) [WS2] Q3 update of donor profiles, pipeline and trackers. [WS4] Analysis note #2 on regional bodies [WS5] PPP opportunity 2: 1 engagement pathway overview
	30 September 2027
	
	
	
	
	
	

	
	Deliverable 10 - Monthly progress report covering all five workstreams (activities completed, outputs shared, issues), plus: [WS5] PPP opportunity 2: proposal / concept note input (WS5) [WS4] Relationship updates with regional bodies [WS5] Begin donor / opportunity analysis and Country Office intelligence support for Q4
	31 October 2027
	
	
	
	
	
	

	
	Deliverable 11 - Monthly progress report covering all five workstreams (activities completed, outputs shared, issues), plus: [WS2] At least 1 Donor or partner profile is developed (Q4) [WS2] Documented Country Office support [WS4] Draft 1 end-of-year summary of regional bodies relationships
	30 November 2027
	
	
	
	
	
	

	
	Deliverable 12 - Monthly progress report covering all five workstreams (activities completed, outputs shared, issues), plus: [WS1] Q4 delivery: At least 1 donor / opportunity analysis, proposals, concept notes or donor reports, and Country Office intelligence support [WS2] Q4 update of donor profiles, pipelines and trackers [WS2, 3] Regional newsletter #2 [WS2] 1 briefing or analysis product (Q4) [WS4] 1 Final end-of-year summary of regional bodies relationships paper [WS2] 1 Annual review/handover note
	31 December 2027
	
	
	
	
	
	

	
	TOTAL AMOUNT 
	
	
	Click here



Note: Shaded cells shall be filled by the Applicants.



Notes to financial offer:
1. Payment will be made on submission and acceptance of deliverables as stated above. UNICEF reserves the right to withhold payment in case the deliverables submitted are not up to the required standard or in case of delays in submitting the deliverables on the part of the consultant.
2. Air travel should be economy class using the most direct route.
3. No other fee would be paid or reimbursed other than the fee indicated in the financial proposal.
4. The consultant will work on own computer(s) and use own office resources and materials in the execution of this assignment, including personal email address(es) and phones. 
5. All pocket expenses including travel will be included in the specific lumpsum deliverables fees and paid as part of satisfactory completion of the deliverables. If the deliverables are not completed or achieved, these costs will not be paid separately.

PAYMENT TERMS: Net 30 days

Name of the Applicant: Click here
Signature of the Applicant: Click here 	
Address:  Click here
Contact no.:  Click here	
Email address:  Click here
Date: Click here
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