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TEMPLATE FOR FINANCIAL PROPOSAL

INDIVIDUAL CONSULTANT FOR National Consultant for end-user monitoring and supply support

Currency of the proposal: USD

	S. No.
	Deliverables
	Deadline for completion of deliverable
	Details of Travel Required
	Professional Fee (Daily)


	Input Days
	Total Professional Fee 
	Total Travel Cost 
	Total Amount (All Inclusive Fee) 

	
	(A)
	(B)
	(C)
	(D)
	(E)
	(F = DxE)
	(G)
	(H = F+G)

	
1.
	Inception package: monitoring methodology, standard school checklist, baseline sheet per school (works scope, supplies delivered, open snag-list and warranty items) and visit schedule. 
	15 January 2027 
	None 

	Click here
	Click here
	Click here
	Click here
	Click here

	2.
	School monitoring reports for 17 schools, with a batch summary and action tracker. Each report covers: supplies (availability, functionality, use, recording on the school’s balance, warranty issues); condition and use of inclusive infrastructure after handover; feedback from directors, teachers and parents; corrective actions with responsible party and deadline; photographs of facilities and equipment. 
	26 February 2027 
	7 trips, 16 days: Tashkent City 1 day (trip 1); Tashkent Region 3 days (trips 2–3); Syrdarya 3 days (trips 3–4); Jizzakh 3 days (trip 5); Samarkand 3 days (trip 6); Navoiy 3 days (trip 7)
	Click here
	Click here
	Click here
	Click here
	

	3.
	Technical packages (specifications or terms of reference, cost estimates, market research and evaluation criteria) for the Education procurement cases in the section’s supply plan for January – February 2027, with case tracker. 
	26 February 2027 
	None
	Click here
	Click here
	Click here
	Click here
	Click here 

	4.
	School monitoring reports in the same format for 17 schools, with a batch summary and updated action tracker. 
	31 March 2027 
	7 trips, 17 days: Bukhara 3 days (trip 8); Kashkadarya 4 days (trips 9–10); Surkhandarya 5 days (trips 11–12); Fergana 5 days (trips 13–14)

	Click here
	Click here
	Click here
	Click here
	

	5.
	School monitoring reports in the same format for 16 schools, with a batch summary and updated action tracker. 
	30 April 2027 
	7 trips, 17 days: Namangan 3 days (trip 15); Andijan 4 days (trips 16–17); Khorezm 4 days (trips 18–19); Republic of Karakalpakstan 6 days (trips 19–21) 
 
	Click here
	Click here
	Click here
	Click here
	

	6.
	Costed standard package (works, equipment and maintenance) based on the actual costs of the 50 schools, with a planning and budgeting tool for use by MOPSE. 
	31 May 2027 
	None
	
	
	
	
	

	7.
	Technical packages for the Education procurement cases planned for March – May 2027; technical inputs to the bid evaluation of package 1 cases; updated case tracker. 
	31 May 2027 
	None
	
	
	
	
	

	8.
	Sustainability and handover plan agreed with MOPSE, and a maintenance guide for school directors (see task 7). 
	30 June 2027 
	None
	
	
	
	
	

	9.
	Second monitoring visit to the five schools in Karakalpakstan and follow-up visits to schools with open corrective actions; updated action tracker with the status of corrective actions in all 50 schools, verified with evidence from the schools. 
	30 June 2027 
	4 trips, 10 days: Republic of Karakalpakstan 6 days (trip 22, second visit to the five schools, 4 days; trip 23, follow-up visit, 2 days); Khorezm 2 days (trip 24, follow-up visit); Surkhandarya 2 days (trip 25, follow-up visit). Destinations of trips 23–25 are indicative, for the financial proposal.
	
	
	
	
	

	10.
	Final consolidated report and presentation to UNICEF and MOPSE (results, lessons learned, recommendations for future projects and specifications); dataset and photo archive. 
	30 June 2027 
	None
	
	
	
	
	

	11.
	Technical packages for the Education procurement cases planned for June 2027; technical inputs to the bid evaluation of package 2 cases; supply and infrastructure annex (scope, costed list of works and supplies, procurement strategy, timeline and risks) to one new education concept note or project proposal; final case tracker. 
	30 June 2027 
	None
	
	
	
	
	

	
	TOTAL AMOUNT 
	
	
	Click here



Note: Shaded cells shall be filled by the Applicants.



Notes to financial offer:
1. Payment will be made on submission and acceptance of deliverables as stated above. UNICEF reserves the right to withhold payment in case the deliverables submitted are not up to the required standard or in case of delays in submitting the deliverables on the part of the consultant.
2. Air travel should be economy class using the most direct route.
3. No other fee would be paid or reimbursed other than the fee indicated in the financial proposal.
4. The consultant will work on own computer(s) and use own office resources and materials in the execution of this assignment, including personal email address(es) and phones. 
5. All pocket expenses including travel will be included in the specific lumpsum deliverables fees and paid as part of satisfactory completion of the deliverables. If the deliverables are not completed or achieved, these costs will not be paid separately.

PAYMENT TERMS: Net 30 days

Name of the Applicant: Click here
Signature of the Applicant: Click here 	
Address:  Click here
Contact no.:  Click here	
Email address:  Click here
Date: Click here
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