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TEMPLATE FOR FINANCIAL PROPOSAL

Transition support consultancy, WASH, UNICEF, Zimbabwe

Currency of the proposal: USD

	S. No.
	Deliverables
	Deadline for completion of deliverable
	Details of Travel Required
	Professional Fee (Daily)


	Input Days
	Total Professional Fee 
	Total Travel Cost 
	Total Amount (All Inclusive Fee) 

	
	(A)
	(B)
	(C)
	(D)
	(E)
	(F = DxE)
	(G)
	(H = F+G)

	1.
	Deliverable 1: Inception report and assignment tracker, including confirmed methodology, consultation schedule, document review, priority risks and detailed delivery plan
	7 December 2026
	1 Economy Fare from origin to Harare
	Click here
	Click here
	Click here
	Click here
	Click here

	2.
	Deliverable 2: 2026 WASH/CEE programme closure and results package, including consolidated results, financial and implementation follow-up, donor-reporting status, lessons and a management action register
	22 December 2026
	
	Click here
	Click here
	Click here
	Click here
	

	3.
	Deliverable 3: Draft 2027 WASH/CEE workplan package, aligned with the 2027-2031 Country Programme and incorporating proposed contributions across all four programme outcomes
	20 January 2027
	

	Click here
	Click here
	Click here
	Click here
	Click here 

	4.
	Deliverable 4: Government and partner consultation package, including presentation materials, consultation record, agreed revisions, responsibilities and a roadmap towards programme integration.
	10 February 2027
	

	Click here
	Click here
	Click here
	Click here
	

	5.
	Deliverable 5: Resource mobilisation and strategic positioning package for WASH, comprising a prioritised funding pipeline and financing approach, partner engagement briefs and at least two concept notes or proposal packages.
	24 February 2027
	
	Click here
	Click here
	Click here
	Click here
	

	6.
	Deliverable 6: Updated WASH emergency preparedness and response action plan, supported by a documented internal readiness review and prioritised corrective actions
	3 March 2027
	
	Click here
	Click here
	Click here
	Click here
	

	7.
	Deliverable 7: Final consultancy report and handover package, including consolidated programme documentation, outstanding actions, key risks, recommendations and a management presentation.
	15 March 2027
	1 Economy Fare from Harare to origin

	Click here
	Click here
	Click here
	Click here
	

	
	TOTAL AMOUNT 
	
	
	Click here



Note: Shaded cells shall be filled by the Applicants.



Notes to financial offer:
1. Payment will be made on submission and acceptance of deliverables as stated above. UNICEF reserves the right to withhold payment in case the deliverables submitted are not up to the required standard or in case of delays in submitting the deliverables on the part of the consultant.
2. Air travel should be economy class using the most direct route.
3. No other fee would be paid or reimbursed other than the fee indicated in the financial proposal.
4. The consultant will work on own computer(s) and use own office resources and materials in the execution of this assignment, including personal email address(es) and phones. 
5. All pocket expenses including travel will be included in the specific lumpsum deliverables fees and paid as part of satisfactory completion of the deliverables. If the deliverables are not completed or achieved, these costs will not be paid separately.

PAYMENT TERMS: Net 30 days

Name of the Applicant: Click here
Signature of the Applicant: Click here 	
Address:  Click here
Contact no.:  Click here	
Email address:  Click here
Date: Click here
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