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TEMPLATE FOR FINANCIAL PROPOSAL

INDIVIDUAL CONSULTANT FOR Consultant for a Heatwave Anticipatory Action Framework in the Philippines

Currency of the proposal: PHP

	S. No.
	Deliverables
	Deadline for completion of deliverable
	Details of Travel Required
	Professional Fee (Daily)


	Input Days
	Total Professional Fee 
	Total Travel Cost 
	Total Amount (All Inclusive Fee) 

	
	(A)
	(B)
	(C)
	(D)
	(E)
	(F = DxE)
	(G)
	(H = F+G)

	
1.
	Inception report with methodology, work plan, stakeholder map, data requirements, desk review findings, consultation tools, coordination plan, validation approach, sequencing of activities, key decision points and pilot contingency arrangements.
	30 November 2026

	NA
	Click here
	Click here
	Click here
	Click here
	Click here

	2.
	Heat risk analysis and pilot site selection report, including heat hazard, exposure and vulnerability analysis; child vulnerability mapping; pilot site selection criteria; shortlist of candidate municipalities; and risk profile of the selected site.
	31 January 2027
	NA
	Click here
	Click here
	Click here
	Click here
	

	3.
	Forecast-based trigger system and performance assessment, including proposed readiness, activation and, where feasible, observational trigger options; focused technical review of trigger approaches, forecast products and early warning methodologies; proposed thresholds, lead times and activation rules; and assessment of forecast performance, reliability, operational feasibility, false alarms and missed events.
	 28 February 2027
	

	Click here
	Click here
	Click here
	Click here
	Click here 

	4.
	 Draft child-focused anticipatory action package, including proposed actions across relevant sectors; targeting criteria; unit costs; supply and partner requirements; delivery channels; start, pause, stop and re activation rules; feasibility assessment; and related AAP, safeguarding, inclusion, MEL, post distribution monitoring and after action review arrangements.
	15 March 2027
	NA

	Click here
	Click here
	Click here
	Click here
	

	5.
	Financing and activation protocol package, including costing assumptions, financing options, activation procedures, decision making process, coordination arrangements, readiness requirements, roles and draft readiness, activation and stand down notices.
	15 March 2027
	NA
	Click here
	Click here
	Click here
	Click here
	

	6.
	Simulation, validation and pilot readiness package, including simulation exercise design and report; findings on triggers, roles, activation pathways, information flows and coordination protocols; documentation of the validation process with the National AA Technical Working Group and the endorsement or adoption process with the pilot LGU DRRM Council, as appropriate, including outcomes; revised pilot-ready Heatwave Anticipatory Action Framework; and pilot implementation and learning plan.
	31 March 2027
	NA
	
	
	
	
	

	7.
	Pilot implementation and learning report documenting pilot preparation, LGU orientation, operational readiness, forecast monitoring, readiness, activation, or stand-down decisions, implementation support, actions delivered by implementing partners, community and partner feedback, preliminary post-distribution monitoring findings, implementation challenges, early results and lessons learned; or, if triggers are not reached, documentation of forecast monitoring, readiness actions, coordination undertaken, and agreed alternative learning activities.
	31 July 2027
	NA
	
	
	
	
	

	8.
	Updated final Heatwave Anticipatory Action Framework reflecting simulation, government validation, pilot documentation, post distribution monitoring findings or readiness findings, and after-action review learning; recommendations for scale-up and integration into government systems, including alignment with RA 12287 and its IRR; final presentation to UNICEF and counterparts; and concise summary brief.
	31 August 2027
	NA
	
	
	
	
	

	
	TOTAL AMOUNT 
	
	
	Click here



Note: Shaded cells shall be filled by the Applicants.



Notes to financial offer:
1. Payment will be made on submission and acceptance of deliverables as stated above. UNICEF reserves the right to withhold payment in case the deliverables submitted are not up to the required standard or in case of delays in submitting the deliverables on the part of the consultant.
2. Air travel should be economy class using the most direct route.
3. No other fee would be paid or reimbursed other than the fee indicated in the financial proposal.
4. The consultant will work on own computer(s) and use own office resources and materials in the execution of this assignment, including personal email address(es) and phones. 
5. All pocket expenses including travel will be included in the specific lumpsum deliverables fees and paid as part of satisfactory completion of the deliverables. If the deliverables are not completed or achieved, these costs will not be paid separately.

PAYMENT TERMS: Net 30 days

Name of the Applicant: Click here
Signature of the Applicant: Click here 	
Address:  Click here
Contact no.:  Click here	
Email address:  Click here
Date: Click here
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