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TEMPLATE FOR FINANCIAL PROPOSAL

INDIVIDUAL CONSULTANT FOR   Construction Supervision Consultant   

Currency of the proposal: USD

	S. No.
	Deliverables
	Deadline for completion of deliverable
	Details of Travel Required
	Professional Fee (Daily)


	Input Days
	Total Professional Fee 
	Total Travel Cost 
	Total Amount (All Inclusive Fee) 

	
	(A)
	(B)
	(C)
	(D)
	(E)
	(F = DxE)
	(G)
	(H = F+G)

	
1.
	Deliverable 1: Baseline assessment report and contract-specific acceleration plans. Cover all initially assigned contracts, documenting verified progress, outstanding works, constraints and dated photographs. Each plan shall specify critical activities, measurable progress targets, resource requirements, material delivery dates, testing milestones, responsible parties and forecast completion dates. 

	Preliminary findings and priority plans by 30 December 2026; complete initial package by 29 January 2027. 

	8 days to travel on Ancuabe, Chiure, Macomia, Palma and Mocimboa da Praia 

	Click here
	Click here
	Click here
	Click here
	Click here

	2.
	Deliverable 2: ESS screening and mitigation package. Provide completed screening forms for all initially assigned locations and a consolidated matrix specifying risks, mitigation measures, responsible parties and deadlines. Screen newly assigned locations within 15 working days of assignment, subject to access. 

	Priority package by 30 January 2027; complete initial coverage by 28 February 2027. 

	8 days to travel on Ancuabe, Chiure, Macomia, Palma and Mocimboa da Praia 

	Click here
	Click here
	Click here
	Click here
	

	3.
	Deliverable 3: Twenty-two biweekly supervision reports and eleven consolidated monthly progress reports. Biweekly reports shall document planned versus actual progress, inspections, dated photographs, quality and ESS findings, and corrective actions. Monthly reports shall consolidate physical and financial progress, contractor performance, risks, completion forecasts and decisions required, including revised acceleration plans for contracts missing agreed targets. 


	Two supervision reports and one consolidated report per reporting month, according to the agreed calendar. 
Final submissions by 29 October 2027. 

	
91 days to travel on Ancuabe, Chiure, Macomia, Palma and Mocimboa da Praia 

	Click here
	Click here
	Click here
	Click here
	Click here 

	4.
	Deliverable 4: Completion and handover assessment package for each assigned contract reaching completion, including inspection findings, defects status, test reviews, documentation checklist and handover recommendation. Include an updated follow-up register for incomplete works. 

	Within 10 working days of each completion inspection. Estimate of 15 projects 
Final status updates by 29 October 2027. 
	
8 days to travel on Ancuabe, Chiure, Macomia, Palma and Mocimboa da Praia 

	Click here
	Click here
	Click here
	Click here
	

	5.
	Deliverable 5: Technical response package for each authorized assessment, comprising findings, priority interventions, BOQs, estimates, specifications and sketches where required. Submit initial findings within two working days and the complete package within five working days after assessment. 

	As requested between 30 November 2026 and 29 October 2027, within the stated turnaround times and assignment end date. 

	8 days to travel on Ancuabe, Chiure, Macomia, Palma and Mocimboa da Praia 

	Click here
	Click here
	Click here
	Click here
	

	6.
	Deliverable 6: Final consultancy report and indexed electronic archive. Cover all assigned contracts, baseline-to-final progress, achievements, effectiveness of acceleration measures, unresolved issues and follow-up responsibilities. Include a documentation completeness checklist. 

	Draft by 15 October 2027; final report and archive by 29 October 2027. 

	3 days to travel on Ancuabe, Chiure, Macomia, Palma and Mocimboa da Praia 

	
	
	
	
	

	
	TOTAL AMOUNT 
	
	
	Click here



Note: Shaded cells shall be filled by the Applicants.



Notes to financial offer:
1. Payment will be made on submission and acceptance of deliverables as stated above. UNICEF reserves the right to withhold payment in case the deliverables submitted are not up to the required standard or in case of delays in submitting the deliverables on the part of the consultant.
2. Air travel should be economy class using the most direct route.
3. No other fee would be paid or reimbursed other than the fee indicated in the financial proposal.
4. The consultant will work on own computer(s) and use own office resources and materials in the execution of this assignment, including personal email address(es) and phones. 
5. All pocket expenses including travel will be included in the specific lumpsum deliverables fees and paid as part of satisfactory completion of the deliverables. If the deliverables are not completed or achieved, these costs will not be paid separately.

PAYMENT TERMS: Net 30 days

Name of the Applicant: Click here
Signature of the Applicant: Click here 	
Address:  Click here
Contact no.:  Click here	
Email address:  Click here
Date: Click here
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